## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KHAIDYA PIPED WATER SUPPLY SCHEME | SM/13946 | New | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 2.56 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KHAIDYA PIPED WATER SUPPLY SCHEME | SM/13946 | New | Material Requisition To Resource Division |  |  | RTOR000376/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 9.37 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KHAIDYA PIPED WATER SUPPLY SCHEME | SM/13946 | New | Material Requisition To Resource Division |  |  | RTOR000723/2023-2024 | 5264/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KHAIDYA PIPED WATER SUPPLY SCHEME | SM/13946 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KHAIDYA PIPED WATER SUPPLY SCHEME | SM/13946 | New | New service connection charges for Khaidya PWSS TW-1 |  |  | BILL/02201/2023-2024 | BP-2023-24-396 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.66 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KHAIDYA PIPED WATER SUPPLY SCHEME | SM/13946 | New | New service connection charges for Khaidya PWSS TW-2 |  |  | BILL/02202/2023-2024 | BP-2023-24-397 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.36 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KHAIDYA PIPED WATER SUPPLY SCHEME | SM/13946 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARASAT, JAGADABAD & KHAIDYA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | J.E. 1 BURDWAN | ORD/000465/2023-2024 | 3460/BWD | 08/08/2023 | 29/09/2025 | CONCORD EMC ENCLAVE LLP | 1526.24 | 183.82 | 12.04 | 5
8 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KHAIDYA PIPED WATER SUPPLY SCHEME | SM/13946 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khaidya Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000657/2023-2024 | 4000/CMD | 29/08/2023 | 01/06/2025 | AHALYA ENGINEERING WORKS | 28.95 | 0 | 0 | 90
Total | [13 empty] | 1655.15 | 183.82 | 11.11