## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-II | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/13947 | New | Material Requisition To Resource Division |  |  | RTOR000468/2023-2024 | 3992/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 12.78 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-II | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/13947 | New | Material Requisition To Resource Division |  |  | RTOR000259/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 15.58 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-II | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/13947 | New | Material Requisition To Resource Division |  |  | RTOR000668/2023-2024 | 5089/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-II | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/13947 | New | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) |  |  | ORD/000985/2023-2024 | 2561/BSD | 30/10/2023 | 04/01/2024 | MD HASIN | 0.85 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-II | Central Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/13947 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and Compound lighting arrangement for Tube well No.- 1 & 2 at GHOSHPUR Water Supply Scheme [BLOCK- MEMARI- 2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001603/2023-2024 | 1533/CMD | 05/03/2024 | 04/05/2024 | CHOUDHURY ENTERPRISE | 28.82 | 22.94 | 79.6 | 75
6 | PURBA BARDHAMAN | Memari-II | Central Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/13947 | New | New service connection at Ghoshpur PWSS TW -1 |  |  | BILL/02330/2023-2024 | BP-2023-24-446 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.28 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-II | Central Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/13947 | New | NEW SERVICE CONNECTION FOR GHOSHPUR PWSS. |  |  | BILL/02701/2023-2024 | BP-2023-24-566 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.97 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-II | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/13947 | New | GHOSHPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000110/2023-2024 | 2299/BWD | 19/05/2023 | 01/01/2026 | MLG CONSTRUCTION | 441.87 | 126.76 | 28.69 | 52
9 | PURBA BARDHAMAN | Memari-II | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME | SM/13947 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2024 to 31-01-2025) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000896/2024-2025 | 2438/BSD | 29/10/2024 | 03/01/2025 | PARVIN BEGAM | 0.85 | 0.28 | 33.33 | 100
Total | [13 empty] | 533.45 | 149.98 | 28.11