## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways for AMARPUR Piped Water Supply Scheme under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000820/2023-2024 | 4952/BWD | 17/11/2023 | 16/11/2024 | SUJAY KUMAR RAY | 344.32 | 145.1 | 42.14 | 50
2 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amarpur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000913/2023-2024 | 4177/CMD | 29/08/2023 | 01/05/2025 | AMUSAR IMPEX PVT. LTD. | 28.55 | 22.63 | 79.28 | 96
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 9.35 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 20.19 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | Material Requisition To Resource Division |  |  | RTOR000611/2023-2024 | 4932/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 30.36 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 80
7 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | Formal Work Order for Additional work for laying 200 mm dia HDPE pipe line and other necessary allied works Amarpur & Bhedia Piped W/S Scheme, Block- Aushgram-2, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2 | ORD/000141/2024-2025 | 1291/DWSD | 06/09/2024 | 04/04/2025 | SAIKAT RAY | 196.61 | 9.11 | 4.63 | 60
8 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | NEW SERVICE CONNECTION FOR AMARPUR PWSS PH 1. |  |  | BILL/02866/2023-2024 | BP-2023-24-604 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | NEW SERVICE CONNECTION FOR AMARPUR PWSS PH 2. |  |  | BILL/02867/2023-2024 | BP-2023-24-605 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.88 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | Annual O and Mtc of distribution syste, rising main, sluice valves including operation of sulice valves at AMRARGAR PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-I | JUNIOR ENGINEER-1 | ORD/000224/2026-2027 | 912/DWSD | 30/06/2026 | 30/06/2027 | B.M. SARKAR | 4.42 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at AMARPUR PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-I | Junior Engineer_3 | ORD/000232/2026-2027 | 881/DWSD | 29/06/2026 | 29/06/2027 | SUJAY KUMAR RAY | 5.1 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | AMARPUR PIPED WATER SUPPLY SCHEME | SM/13967 | New | Annual Operation and maintenance of different dia MS/DI rising main pipe line from Intake well site to Panagarh Industrial Park H/W site under Surface based PWSS for Panagarh Industrial Park, of Durgapur W/s Division,PHE Dte (w.e.f 01.08.2026 to 31.07.2027) | Assistant Engineer-I | JUNIOR ENGINEER-1,Junior Engineer_3 | ORD/000286/2026-2027 | 1102/DWSD | 31/07/2026 | 31/07/2027 | S. ROY AND ASSOCIATES | 29 | 0 | 0 | 0
Total | [13 empty] | 769.42 | 176.85 | 22.98