## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | EORA PIPED WATER SUPPLY SCHEME | SM/13968 | New | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 23.59 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | EORA PIPED WATER SUPPLY SCHEME | SM/13968 | New | Material Requisition To Resource Division |  |  | RTOR000750/2023-2024 | 5249/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 18.5 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | EORA PIPED WATER SUPPLY SCHEME | SM/13968 | New | Material Requisition To Resource Division |  |  | RTOR000443/2023-2024 | 3833/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 3.71 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Central Mechanical | EORA PIPED WATER SUPPLY SCHEME | SM/13968 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | EORA PIPED WATER SUPPLY SCHEME | SM/13968 | New | NEW SERVICE CONNECTION FOR EORA PWSS |  |  | BILL/02596/2023-2024 | BP-2023-24-548 | 20/02/2024 | 20/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.64 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | EORA PIPED WATER SUPPLY SCHEME | SM/13968 | New | NEW SERVICE CONNECTION FOR EORA PWSS TW -1. |  |  | BILL/03102/2023-2024 | BP-2023-24-642 | 15/03/2024 | 15/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.54 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Burdwan Division | EORA PIPED WATER SUPPLY SCHEME | SM/13968 | New | EORA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer ,JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000062/2023-2024 | 1936/BWD | 24/04/2023 | 05/09/2025 | TUSHAR KANTI GHOSH | 79.02 | 49.97 | 63.24 | 100
8 | PURBA BARDHAMAN | Bhatar | Central Mechanical | EORA PIPED WATER SUPPLY SCHEME | SM/13968 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Eora Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000746/2023-2024 | 4056/CMD | 29/08/2023 | 15/05/2026 | SUNRISE ENGINEERING CORPORATION | 26.98 | 20.94 | 77.62 | 90
9 | PURBA BARDHAMAN | Bhatar | Burdwan Division | EORA PIPED WATER SUPPLY SCHEME | SM/13968 | New | Road Restoration for Eora PWSS in Bhatar Block under Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. |  | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000429/2024-2025 | 624/DSD | 05/08/2024 | 04/09/2024 | KOHINOOR CONSTRUCTION CO. | 5.38 | 0 | 0 | 0
Total | [13 empty] | 249.35 | 70.9 | 28.44