## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN | SM/14014 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of NASARATPUR Piped Water Supply Scheme at Gopinathpur (Part), Nasaratput (Part) & Paruldanga (Part) Village (Mouza), Purbasthali - I Block under Burdwan Division, PHE Dte | Assistant Engineer |  | ORD/000372/2021-2022 | 211/BWD | 11/01/2022 | 12/03/2022 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 76.77 | 59.72 | 77.8 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN | SM/14014 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000337/2024-2025 | 3017/BWD | 05/08/2024 | 19/10/2024 | HORIZEN | 38 | 13.64 | 35.89 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN | SM/14014 | Augmentation | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL UNDER NASARATPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001142/2023-2024 | 1978/KSD | 09/02/2024 | 19/02/2024 | BISWAS ENTERPRISE | 0.66 | 0.66 | 99.45 | 100
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN | SM/14014 | Augmentation | New service connection for Augmentation of Nasratpur PWSS TW-2. |  |  | BILL/02397/2023-2024 | BP-2023-24-509 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.21 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN | SM/14014 | Augmentation | New service connection for augmentation of Nasratpur PH-I PWSS. |  |  | BILL/00085/2024-2025 | BP-2024-25-30 | 19/04/2024 | 19/04/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.19 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN | SM/14014 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 3 & 4 at Augumentation of NASRATPUR Water Supply Scheme [BLOCK- PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001613/2023-2024 | 1544/CMD | 05/03/2024 | 01/06/2025 | MS DAS ELECTRIC CO | 24.63 | 11.7 | 47.52 | 95
7 | PURBA BARDHAMAN |  | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN | SM/14014 | Augmentation | Different types of works involve in connection with Augmentation of NASRATPUR PWSS (SM/14014), Purbasthali-I Block, under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001098/2024-2025 | 432/BWD | 20/01/2025 | 20/05/2025 | SANDIP BISWAS | 199.5 | 0 | 0 | 0
Total | [13 empty] | 357.97 | 85.73 | 23.95