## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 56.53 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | Material Requisition To Resource Division |  |  | RTOR000311/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 19.47 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | Material Requisition To Resource Division |  |  | RTOR000584/2023-2024 | 4928/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 34.57 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Central Mechanical | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | New service connection charges for Chhatini PWSS TW-1 |  |  | BILL/01049/2023-2024 | BP-2023-24-118 | 16/08/2023 | 16/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.96 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | New Service connection at CHHATINI PWSS TW-2. |  |  | BILL/02368/2023-2024 | BP-2023-24-480 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.24 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | CHHATINI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000093/2023-2024 | 2216/BWD | 15/05/2023 | 01/04/2025 | SHWET BARANI | 539.35 | 0 | 0 | 55
8 | PURBA BARDHAMAN | Bhatar | Central Mechanical | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chhatini Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000212/2023-2024 | 3069/CMD | 21/07/2023 | 20/08/2023 | SUNRISE ENGINEERING CORPORATION | 27.79 | 0 | 0 | 60
9 | PURBA BARDHAMAN | Bhatar | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day [Period February'2024 to April'2024] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001233/2023-2024 | 91/DSD | 31/01/2024 | 18/04/2024 | MD HASIN | 1 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Bhatar | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | Providing Functional Household Tap Connection (FHTC) by sinking of tube well 250 x 150 mm. dia., Constn. of Pump House & Boundary Wall within command area of CHHATINI W/S. Scheme, Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000401/2024-2025 | 3033/BWD | 06/08/2024 | 04/12/2024 | SAHA CONSTRUCTION & CO. | 129.06 | 0 | 0 | 50
11 | PURBA BARDHAMAN | Bhatar | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME | SM/14017 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period May'2024 to July'2024] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000255/2024-2025 | 369/DSD | 30/04/2024 | 17/07/2024 | MD HASIN | 1 | 0 | 0 | 0
Total | [13 empty] | 896.97 | 0 | 0