## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-II | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME | SM/14019 | New | Material Requisition To Resource Division |  |  | RTOR000351/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 13.72 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-II | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME | SM/14019 | New | Material Requisition To Resource Division |  |  | RTOR000428/2023-2024 | 3836/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 2.35 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-II | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME | SM/14019 | New | Material Requisition To Resource Division |  |  | RTOR000680/2023-2024 | 5064/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-II | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME | SM/14019 | New | NANDIARA Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 200 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site under Memari-II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000487/2023-2024 | 3502/BWD | 10/08/2023 | 30/06/2025 | S.S.S. ENTERPRISES | 451.06 | 0 | 0 | 45
5 | PURBA BARDHAMAN | Memari-II | Central Mechanical | NANDIARA PIPED WATER SUPPLY SCHEME | SM/14019 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 31/10/2024 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-II | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME | SM/14019 | New | Supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-02-2024 to 30-04-2024) | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001181/2023-2024 | 188/BSD | 31/01/2024 | 06/04/2024 | PARVIN BEGAM | 0.85 | 0 | 0 | 97
7 | PURBA BARDHAMAN | Memari-II | Central Mechanical | NANDIARA PIPED WATER SUPPLY SCHEME | SM/14019 | New | New service connection for NANDIARA PWSS TW 2. |  |  | BILL/02443/2023-2024 | BP-2023-24-520 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.33 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-II | Central Mechanical | NANDIARA PIPED WATER SUPPLY SCHEME | SM/14019 | New | New service connection for NANDIARA PWSS TW 1. |  |  | BILL/02442/2023-2024 | BP-2023-24-521 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.76 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-II | Central Mechanical | NANDIARA PIPED WATER SUPPLY SCHEME | SM/14019 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nandiara Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000715/2023-2024 | 4026/CMD | 29/08/2023 | 01/06/2025 | JAGANNATH ENTERPRISE | 29.39 | 0 | 0 | 50
10 | PURBA BARDHAMAN | Memari-II | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME | SM/14019 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-12-2024 to 28-02-2025 |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001043/2024-2025 | 2636/BSD | 29/11/2024 | 27/02/2025 | SK. ASFIA | 1.2 | 0 | 0 | 60
Total | [13 empty] | 567.09 | 0 | 0