## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/14021 | New | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 1241/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 3.55 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/14021 | New | Material Requisition To Resource Division |  |  | RTOR000477/2023-2024 | 4001/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.09 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/14021 | New | Damage restoration charges in connection with WBSEDCL electrification under Rajapur PWSS |  |  | BILL/01477/2023-2024 | BP-2023-24-176 | 29/09/2023 | 29/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.1 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/14021 | New | New service connection charges for Rajapur PWSS TW-1 |  |  | BILL/01090/2023-2024 | BP-2023-24-120 | 17/08/2023 | 17/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.97 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/14021 | New | New service connection charges for Rajapur PWSS TW-2 |  |  | BILL/01091/2023-2024 | BP-2023-24-121 | 17/08/2023 | 17/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.51 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/14021 | New | Material Requisition To Resource Division |  |  | RTOR000807/2023-2024 | 298/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 8.86 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/14021 | New | Addl. New service connection charges for Rajapur PWSS TW-1 |  |  | BILL/01730/2023-2024 | BP-2023-24-245 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.76 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/14021 | New | RAJAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000656/2022-2023 | 359/BWD | 30/01/2023 | 02/07/2024 | PABITRA KUMAR SAMANTA | 116.35 | 92.7 | 79.68 | 90
9 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/14021 | New | Laying of rising main along with crossing of pipeline by HDD/Jack pushing method with other allied work in connection with augmentation of Ganganandapur PWSS (SM/09411) & Rajapur PWSS (SM/ 14021), Purbasthali-I block under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000278/2024-2025 | 2710/BWD | 11/07/2024 | 01/04/2025 | MANASH GHOSH | 81.34 | 65.34 | 80.33 | 60
10 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/14021 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at RAJAPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000053/2023-2024 | 2516/CMD | 02/06/2023 | 02/07/2023 | M/S GHOSH ENTERPRISE | 20.8 | 12.62 | 60.7 | 90
Total | [13 empty] | 250.33 | 170.66 | 68.17