## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | Material Requisition To Resource Division |  |  | RTOR000080/2022-2023 | 1238/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 2.16 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | Material Requisition To Resource Division |  |  | RTOR000752/2023-2024 | 5247/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 18.5 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | New service connection charges for Mandardihi PWSS TW-2 |  |  | BILL/01420/2023-2024 | BP-2023-24-148 | 31/08/2023 | 31/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.15 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | New service connection charges for Mandardihi PWSS TW-1 |  |  | BILL/01050/2023-2024 | BP-2023-24-119 | 17/08/2023 | 17/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.61 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MANDARDIHI Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000359/2023-2024 | 3504/CMD | 31/07/2023 | 29/05/2025 | S.K. ELECTRICALS | 26.96 | 18.81 | 69.78 | 90
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | MANDARDIHI (PART:-B) Piped Water Supply Scheme with LDS & FHTC [NODE POINT 49 TO 77] under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000717/2022-2023 | 919/BWD | 02/03/2023 | 01/04/2023 | PAPRI HAZRA | 18.89 | 17.17 | 90.89 | 100
8 | PURBA BARDHAMAN | Bhatar | Burdwan Division | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | MANDARDIHI (PART:-A) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000719/2022-2023 | 928/BWD | 02/03/2023 | 01/05/2023 | DUBE ENTERPRISE | 63.01 | 63 | 99.99 | 30
9 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | Emergency installation (for urgent FHTC) at Mandardihi Water Supply Scheme PH 2 (part-3) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001676/2023-2024 | 83/CMSD | 15/01/2024 | 27/01/2024 | CHOUDHURY ENTERPRISE | 0.92 | 0.92 | 100 | 100
10 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | Supply and delivery of different Electro-mechanical items (for urgent FHTC) for Mandardihi Water Supply Scheme PH 2 (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001748/2023-2024 | 19/CMSD | 04/01/2024 | 14/01/2024 | CHOUDHURY ENTERPRISE | 0.91 | 0.91 | 100 | 100
11 | PURBA BARDHAMAN | Bhatar | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME | SM/14052 | New | Supply and delivery of submersible pumping machinery (for urgent FHTC) for mandardihi Water Supply Scheme PH 2 (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001672/2023-2024 | 66/CMSD | 11/01/2024 | 23/01/2024 | CHOUDHURY ENTERPRISE | 0.81 | 0.81 | 100 | 100
Total | [13 empty] | 222.92 | 101.62 | 45.59