## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Material Requisition To Resource Division |  |  | RTOR000111/2022-2023 | 1645/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 14.26 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 1259/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 17.21 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | New service connection charges for Kalikapur PWSS TW-1 |  |  | BILL/01444/2023-2024 | BP-2023-24-155 | 07/09/2023 | 07/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | New service connection charges for Kalikapur PWSS TW-2 |  |  | BILL/01469/2023-2024 | BP-2023-24-170 | 27/09/2023 | 27/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kalikapur Water Supply Scheme [ Block- Katwa-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000596/2023-2024 | 3953/CMD | 24/08/2023 | 23/09/2023 | M/S, S.S. ENTERPRISE. | 29.61 | 23.4 | 79.02 | 90
6 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000683/2024-2025 | 1009/KTS | 19/07/2024 | 17/09/2024 | AJIT SAMANTA | 0.77 | 0.23 | 30 | 100
7 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | KALIKAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000732/2022-2023 | 1047/BWD | 09/03/2023 | 01/11/2025 | PASCON | 629.59 | 351.46 | 55.82 | 67
9 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Balance work of OHR, Functional Household Tap Connection, Road restoration etc. for Kalikapur PWSS under KATWA -II Block under Katwa Sub-Division under Burdwan Division, PHED, District:- Purba-Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001040/2024-2025 | 192/BWD | 08/01/2025 | 01/11/2026 | PASCON | 57.78 | 0 | 0 | 90
10 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Balance work such as left out FHTC, Laying of HDPE pipeline, road restoration and other ancillary work for Kalipakur PWSS (SM/14053) under Katwa I Block under Katwa Sub Division under Burdwan Division, PHE. Dte. Dist. Purba Bardhaman. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000947/2025-2026 | 1671/BWD | 11/06/2025 | 11/07/2025 | PASCON | 34.63 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME | SM/14053 | New | Continuation work order for Hiring of one no Diesel Motor Cab (BS-VI) including the cost of fuel . mobile & other charges for the inspection of the different projects of JJM for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. (Period:- 01/09/2025 to 28/02/2026) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000723/2025-2026 | 1907/KTS | 01/09/2025 | 01/03/2026 | HAMID SK | 1.84 | 0 | 0 | 70
Total | [13 empty] | 848.38 | 375.09 | 44.21