## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME | SM/14054 | New | Material Requisition To Resource Division |  |  | RTOR000062/2022-2023 | 1246/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 17.02 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME | SM/14054 | New | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 1638/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 1.1 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME | SM/14054 | New | New service connection charges for Jagadanandapur PWSS TW-2 |  |  | BILL/00797/2023-2024 | BP-2023-24-85 | 26/07/2023 | 26/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.95 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME | SM/14054 | New | New service connection charges for Jagadanandapur W/S Scheme TW-1 |  |  | BILL/00694/2023-2024 | BP-2023-24-36 | 27/06/2023 | 27/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.38 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME | SM/14054 | New | JAGADANANDAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000711/2022-2023 | 777/BWD | 24/02/2023 | 01/01/2025 | MANASH GHOSH | 562.08 | 469 | 83.44 | 78
6 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME | SM/14054 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000683/2024-2025 | 1009/KTS | 19/07/2024 | 17/09/2024 | AJIT SAMANTA | 0.77 | 0.17 | 21.67 | 100
7 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME | SM/14054 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME | SM/14054 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jagadanandapur Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000126/2023-2024 | 2659/CMD | 16/06/2023 | 16/07/2023 | PADMA ENGINEERING CO. | 28.97 | 21.56 | 74.43 | 60
9 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME | SM/14054 | New | Material Requisition To Resource Division |  |  | RTOR000786/2023-2024 | 327/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 22.74 | 0 | 0 | 0
Total | [13 empty] | 692.21 | 490.73 | 70.89