## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | SRIBATI PIPED WATER SUPPLY SCHEME | SM/14055 | New | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day.(Sl No-1) |  |  | ORD/000510/2023-2024 | 499/KTS | 22/05/2023 | 31/07/2023 | M/S MUNMUN DEY | 0.9 | 0 | 0 | 100
2 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | SRIBATI PIPED WATER SUPPLY SCHEME | SM/14055 | New | Material Requisition To Resource Division |  |  | RTOR000110/2022-2023 | 1633/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 9.14 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | SRIBATI PIPED WATER SUPPLY SCHEME | SM/14055 | New | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 1258/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 17.24 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | SRIBATI PIPED WATER SUPPLY SCHEME | SM/14055 | New | New service connection charges for Sribati PWSS TW-2 |  |  | BILL/00755/2023-2024 | BP-2023-24-61 | 17/07/2023 | 17/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.58 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | SRIBATI PIPED WATER SUPPLY SCHEME | SM/14055 | New | New service connection charges for SribatiPWSS TW-1 |  |  | BILL/00881/2023-2024 | BP-2023-24-111 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.83 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | SRIBATI PIPED WATER SUPPLY SCHEME | SM/14055 | New | SRIBATI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000710/2022-2023 | 776/BWD | 24/02/2023 | 31/07/2026 | MANASH GHOSH | 629.32 | 217.16 | 34.51 | 80
7 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | SRIBATI PIPED WATER SUPPLY SCHEME | SM/14055 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sribati Water Supply Scheme [ Block- Katwa-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000059/2023-2024 | 2520/CMD | 02/06/2023 | 02/07/2023 | S.K. ELECTRICALS | 29.6 | 0 | 0 | 48
8 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | SRIBATI PIPED WATER SUPPLY SCHEME | SM/14055 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | SRIBATI PIPED WATER SUPPLY SCHEME | SM/14055 | New | Material Requisition To Resource Division |  |  | RTOR000787/2023-2024 | 321/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 26.68 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | SRIBATI PIPED WATER SUPPLY SCHEME | SM/14055 | New | SUPPLY AND INSTALLATION WORKS FOR SRIBATI PWSS |  |  | BILL/02622/2023-2024 | BP-2023-24-559 | 21/02/2024 | 21/02/2024 | S.K. ELECTRICALS | 23.73 | 0 | 0 | 0
Total | [13 empty] | 796.2 | 217.16 | 27.27