## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME | SM/14057 | New | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 14.84 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME | SM/14057 | New | Material Requisition To Resource Division |  |  | RTOR000630/2023-2024 | 4882/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 26 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME | SM/14057 | New | Material Requisition To Resource Division |  |  | RTOR000493/2023-2024 | 4017/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 23.3 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AKHRA PIPED WATER SUPPLY SCHEME | SM/14057 | New | New service connection charges for Akhra PWSS TW-1 |  |  | BILL/00756/2023-2024 | BP-2023-24-56 | 17/07/2023 | 17/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.96 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AKHRA PIPED WATER SUPPLY SCHEME | SM/14057 | New | New service connection charges for Akhra PWSS TW-2 |  |  | BILL/00757/2023-2024 | BP-2023-24-57 | 17/07/2023 | 17/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.39 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME | SM/14057 | New | AKHARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000011/2023-2024 | 1725/BWD | 13/04/2023 | 01/01/2025 | MANASH GHOSH | 455.23 | 0 | 0 | 78
7 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AKHRA PIPED WATER SUPPLY SCHEME | SM/14057 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AKHRA PIPED WATER SUPPLY SCHEME | SM/14057 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.- 01/11/2023 to 31/12/2023. [Under JJM Works]. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001302/2023-2024 | 859/CMSD | 30/10/2023 | 30/12/2023 | SUBRATA BHADRA | 0.8 | 0 | 0 | 100
9 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | AKHRA PIPED WATER SUPPLY SCHEME | SM/14057 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Akhra Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000135/2023-2024 | 2760/CMD | 28/06/2023 | 29/03/2024 | CHOUDHURY ENTERPRISE | 27.73 | 0 | 0 | 40
Total | [13 empty] | 605.42 | 0 | 0