## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MULGRAM PIPED WATER SUPPLY SCHEME | SM/14058 | New | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 1630/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 1.65 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MULGRAM PIPED WATER SUPPLY SCHEME | SM/14058 | New | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 1236/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 13.55 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MULGRAM PIPED WATER SUPPLY SCHEME | SM/14058 | New | Material Requisition To Resource Division |  |  | RTOR000637/2023-2024 | 5092/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 24.47 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MULGRAM PIPED WATER SUPPLY SCHEME | SM/14058 | New | New service connection charges for Mulgram W/S Scheme TW-1 |  |  | BILL/00695/2023-2024 | BP-2023-24-37 | 27/06/2023 | 27/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.76 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MULGRAM PIPED WATER SUPPLY SCHEME | SM/14058 | New | MULGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000685/2022-2023 | 482/BWD | 08/02/2023 | 08/02/2024 | RADIANT | 475.42 | 465.16 | 97.84 | 98
6 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | MULGRAM PIPED WATER SUPPLY SCHEME | SM/14058 | New | Balance work of OHR, construction Concrete Road, Functional Household Tap Connection, Road restoration etc. for Mulgram PWSS, under KATWA -II Block under Katwa Sub-Division under Burdwan Division, PHED, District:- Purba-Bardhaman. | Assistant Engineer |  | ORD/000502/2024-2025 | 3157/BWD | 22/08/2024 | 20/11/2024 | RADIANT | 66.62 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MULGRAM PIPED WATER SUPPLY SCHEME | SM/14058 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MULGRAM PIPED WATER SUPPLY SCHEME | SM/14058 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000602/2024-2025 | 3106/CMD | 11/12/2024 | 09/02/2025 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MULGRAM PIPED WATER SUPPLY SCHEME | SM/14058 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Mulgram Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000049/2023-2024 | 2511/CMD | 02/06/2023 | 02/07/2023 | M/S. S.R. ENTERPRISE | 28.96 | 22.84 | 78.86 | 40
10 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | MULGRAM PIPED WATER SUPPLY SCHEME | SM/14058 | New | New service connection charges for Mulgram PWSS TW-2 |  |  | BILL/01763/2023-2024 | BP-2023-24-273 | 21/12/2023 | 21/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0 | 0
Total | [13 empty] | 683.47 | 487.99 | 71.4