## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NABASTA PIPED WATER SUPPLY SCHEME | SM/14059 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 80.57 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NABASTA PIPED WATER SUPPLY SCHEME | SM/14059 | New | Material Requisition To Resource Division |  |  | RTOR000348/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 3.49 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NABASTA PIPED WATER SUPPLY SCHEME | SM/14059 | New | Material Requisition To Resource Division |  |  | RTOR000604/2023-2024 | 4931/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 33.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Central Mechanical | NABASTA PIPED WATER SUPPLY SCHEME | SM/14059 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | NABASTA PIPED WATER SUPPLY SCHEME | SM/14059 | New | New Service connection at Nabastha PWSS PH-1 |  |  | BILL/02316/2023-2024 | BP-2023-24-456 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.04 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | NABASTA PIPED WATER SUPPLY SCHEME | SM/14059 | New | New Service connection at Nabastha PWSS PH-2 |  |  | BILL/02317/2023-2024 | BP-2023-24-457 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.95 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Central Mechanical | NABASTA PIPED WATER SUPPLY SCHEME | SM/14059 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at NABASTA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000776/2023-2024 | 4070/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 27.79 | 14.92 | 53.68 | 40
8 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NABASTA PIPED WATER SUPPLY SCHEME | SM/14059 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NABASTA, PASHALA & POALKURA Piped Water Supply Scheme under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000739/2023-2024 | 4652/BWD | 31/10/2023 | 16/04/2026 | STARCO CONSTRUCTIONS | 900.17 | 100.31 | 11.14 | 2
9 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NABASTA PIPED WATER SUPPLY SCHEME | SM/14059 | New | Providing Parallal LDS (Node- 30-43-42-41-49 to 36) & 4nos ICDS connection for at Palsa-Chandrasekharpara within Nabastha PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001068/2024-2025 | 358/BWD | 16/01/2025 | 17/03/2025 | PRATIVA CONSTRUCTION | 7.61 | 0 | 0 | 0
Total | [13 empty] | 1144.69 | 115.23 | 10.07