## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME | SM/14061 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at POALKURA Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000917/2023-2024 | 4181/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 27.65 | 14.46 | 52.29 | 40
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | POALKURA PIPED WATER SUPPLY SCHEME | SM/14061 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NABASTA, PASHALA & POALKURA Piped Water Supply Scheme under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000739/2023-2024 | 4652/BWD | 31/10/2023 | 16/04/2026 | STARCO CONSTRUCTIONS | 900.17 | 82.83 | 9.2 | 2
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | POALKURA PIPED WATER SUPPLY SCHEME | SM/14061 | New | Material Requisition To Resource Division |  |  | RTOR000372/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 15.26 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Burdwan Division | POALKURA PIPED WATER SUPPLY SCHEME | SM/14061 | New | Material Requisition To Resource Division |  |  | RTOR000753/2023-2024 | 5239/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 18.5 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Burdwan Division | POALKURA PIPED WATER SUPPLY SCHEME | SM/14061 | New | Material Requisition To Resource Division |  |  | RTOR000555/2023-2024 | 4948/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 1.3 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME | SM/14061 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME | SM/14061 | New | Additional quotation for new service connection for POALKURA PWSS PH1 |  |  | BILL/01221/2024-2025 | BP-2024-25-418 | 16/12/2024 | 16/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.5 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Bhatar | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME | SM/14061 | New | New service connection for Poalkora PWSS |  |  | BILL/02560/2023-2024 | BP-2023-24-545 | 19/02/2024 | 19/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.14 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Bhatar | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME | SM/14061 | New | New service connection for Poalkura PWSS |  |  | BILL/02842/2023-2024 | BP-2023-24-590 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.85 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Bhatar | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME | SM/14061 | New | New Service connection at Poalkura PWSS PH-1 |  |  | BILL/02319/2023-2024 | BP-2023-24-455 | 30/01/2024 | 30/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.32 | 0 | 0 | 0
Total | [13 empty] | 1060.68 | 97.29 | 9.17