## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KOTALGHOSH PIPED WATER SUPPLY SCHEME | SM/14062 | New | Material Requisition To Resource Division |  |  | RTOR000113/2023-2024 | 1965/BWD | 26/04/2023 | 26/04/2023 | Resource Division | 1.92 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KOTALGHOSH PIPED WATER SUPPLY SCHEME | SM/14062 | New | Material Requisition To Resource Division |  |  | RTOR000387/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 1.48 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KOTALGHOSH PIPED WATER SUPPLY SCHEME | SM/14062 | New | New service connection charges for Kotalghosh PWSS TW-1 |  |  | BILL/01482/2023-2024 | BP-2023-24-183 | 04/10/2023 | 04/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.28 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KOTALGHOSH PIPED WATER SUPPLY SCHEME | SM/14062 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KOTALGHOSH PIPED WATER SUPPLY SCHEME | SM/14062 | New | Material Requisition To Resource Division |  |  | RTOR000812/2023-2024 | 306/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 20.47 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KOTALGHOSH PIPED WATER SUPPLY SCHEME | SM/14062 | New | NEW SERVICE CONNECTION FOR KOTALGHOSH PWSS TW 2. |  |  | BILL/02487/2023-2024 | BP-2023-24-540 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.46 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KOTALGHOSH PIPED WATER SUPPLY SCHEME | SM/14062 | New | Additional quotation in second time against additional works at Kotalghosh PWSS TW-2. |  |  | BILL/00699/2024-2025 | BP-2024-25-269 | 23/08/2024 | 23/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.87 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KOTALGHOSH PIPED WATER SUPPLY SCHEME | SM/14062 | New | KOTALGHOSH Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000498/2023-2024 | 3528/BWD | 10/08/2023 | 01/04/2025 | BRINDABAN KONAR | 325.17 | 271.02 | 83.35 | 5
9 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KOTALGHOSH PIPED WATER SUPPLY SCHEME | SM/14062 | New | Continuation work order for Hiring of one no Diesel Motor Cab (BS-VI) including the cost of fuel . mobile & other charges for the inspection of the different projects of JJM for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. (Period:- 01/09/2025 to 28/02/2026) |  |  | ORD/000723/2025-2026 | 1907/KTS | 01/09/2025 | 01/03/2026 | HAMID SK | 1.84 | 0 | 0 | 0
Total | [13 empty] | 427.55 | 271.02 | 63.39