## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KASHIARA PIPED WATER SUPPLY SCHEME | SM/14075 | New | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 1.83 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KASHIARA PIPED WATER SUPPLY SCHEME | SM/14075 | New | Material Requisition To Resource Division |  |  | RTOR000317/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 7.97 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KASHIARA PIPED WATER SUPPLY SCHEME | SM/14075 | New | Material Requisition To Resource Division |  |  | RTOR000722/2023-2024 | 5265/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KASHIARA PIPED WATER SUPPLY SCHEME | SM/14075 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kashiara Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000656/2023-2024 | 3999/CMD | 29/08/2023 | 28/09/2023 | MENAKA ENTERPRISE. | 28.98 | 22.53 | 77.73 | 90
5 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KASHIARA PIPED WATER SUPPLY SCHEME | SM/14075 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KASHIARA PIPED WATER SUPPLY SCHEME | SM/14075 | New | New service connection for Kashiara W/S Scheme. |  |  | BILL/02189/2023-2024 | BP-2023-24-384 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.91 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | KASHIARA PIPED WATER SUPPLY SCHEME | SM/14075 | New | New service connection charges for Kashiara PWSS TW-2 |  |  | BILL/02207/2023-2024 | BP-2023-24-398 | 17/01/2024 | 17/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.22 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | KASHIARA PIPED WATER SUPPLY SCHEME | SM/14075 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch room, boundary walls with gates, land development, surface drains and internal pathways at different TW site for KASHIARA Piped Water Supply Scheme under BURDWAN I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000480/2023-2024 | 256/BWD | 09/08/2023 | 22/11/2025 | PUSPA ENTERPRISE | 597.52 | 240.68 | 40.28 | 70
Total | [13 empty] | 719.45 | 263.21 | 36.58