## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | Continuation order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.-01/09/2023 to 31/10/2023 [JJM Works]. | ASSISTANT ENGINEER |  | ORD/000851/2023-2024 | 734/CMSD-I | 29/08/2023 | 29/10/2023 | SUBRATA BHADRA | 0.79 | 0 | 0 | 50
2 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 49.01 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | Material Requisition To Resource Division |  |  | RTOR000188/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 12.47 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | Material Requisition To Resource Division |  |  | RTOR000568/2023-2024 | 4940/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 39.83 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | New service connection charges for Utra PWSS TW 1 |  |  | BILL/00815/2023-2024 | BP-2023-24-91 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.03 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | New service connection charges for Utra PWSS TW 2 |  |  | BILL/00812/2023-2024 | BP-2023-24-90 | 28/07/2023 | 28/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.59 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | UTRA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000009/2023-2024 | 1698/BWD | 12/04/2023 | 11/04/2024 | M/S S.S. ENTERPRISE | 487.32 | 0 | 0 | 87
8 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 31/10/2024 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at UTRA Water Supply Scheme [ Block- KALNA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000140/2023-2024 | 2857/CMD | 05/07/2023 | 04/08/2023 | SOUNAK ENTERPRISE | 28.48 | 0 | 0 | 90
10 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | Supply and Delivery of standby Chlorination System for Utra PH 1 & others Water Supply Scheme under CMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001598/2023-2024 | 812/CMSD | 04/10/2023 | 03/11/2023 | SUBRATA BHADRA | 0.9 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | Supply and Delivery of standby Chlorination System for Utra PH 2 & others Water Supply Scheme under CMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001599/2023-2024 | 813/CMSD | 04/10/2023 | 03/11/2023 | SUBRATA BHADRA | 0.9 | 0 | 0 | 100
12 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | Standby Pump Motor set for Utra PH 2 Water Supply Scheme under CMD, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001662/2023-2024 | 1074/CMSD | 15/12/2023 | 27/12/2023 | M/S. S.D. CONSTRUCTION | 0.84 | 0 | 0 | 100
13 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME | SM/14077 | New | Standby Pump Motor set for UTRA PH 1 water supply scheme under CMD,PHE,Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/001729/2023-2024 | 1076/CMSD | 15/12/2023 | 30/12/2023 | SUDIKSHA CONSTRUCTION | 0.84 | 0 | 0 | 100
Total | [13 empty] | 682.42 | 0 | 0