## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 1965/BWD | 26/04/2023 | 26/04/2023 | Resource Division | 7.15 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Material Requisition To Resource Division |  |  | RTOR000733/2023-2024 | 5235/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 21.07 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 5.01 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | New service connection charges for Saranga PWSS TW-2 |  |  | BILL/00800/2023-2024 | BP-2023-24-87 | 26/07/2023 | 26/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.97 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | New service connection charges for Saranga PWSS TW-1 |  |  | BILL/00818/2023-2024 | BP-2023-24-94 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.5 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Continuation order-Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven ) for supervision of site for the office of the Assistant Engineer,under CMD,PHE,Dte. [W.e.f-01/03/2024 to 29/04/2024) | ASSISTANT ENGINEER | Junior Engineer | ORD/001914/2023-2024 | 359/CMSD | 27/02/2024 | 27/04/2024 | SUBRATA BHADRA | 0.79 | 0.79 | 99.81 | 100
7 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Supply & delivery of submersible pumping machinery (for urgent FHTC) for Tube well no.-1 at Saranga w/s scheme, (Block -Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001663/2023-2024 | 1075/CMSD | 15/12/2023 | 27/12/2023 | SUBHRA ENTERPRISE | 0.67 | 0.67 | 100 | 100
8 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Supply & delivery of different electro-mechanical accessories (for urgent FHTC) for Tube well no.-1 at Saranga w/s scheme, ( Block -Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/001664/2023-2024 | 1073/CMSD | 15/12/2023 | 25/12/2023 | SUBHRA ENTERPRISE | 0.8 | 0.77 | 97.15 | 100
9 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Emergency Installation (for urgent FHTC) of departmental supply submersible pumping machinery with supply main switch, cable, starter etc. for Tube well no.-1 at Saranga w/s scheme, ( Block -Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/001666/2023-2024 | 06/CMSD | 02/01/2024 | 12/01/2024 | SUBHRA ENTERPRISE | 0.72 | 0.68 | 95.67 | 100
10 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SARANGA & KAMALPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000082/2023-2024 | 2078/BWD | 04/05/2023 | 01/04/2025 | KHAN ENTERPRISE | 820.73 | 249.61 | 30.41 | 42
11 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Balance work for providing Functional Household Tap Connection (FHTC) within command area SARANGA W/S. Scheme of Khandaghosh Block under Burdwan Divn., PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001097/2024-2025 | 431/BWD | 20/01/2025 | 20/05/2025 | ANWESHA CONSTRUCTION | 98.39 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 31/10/2024 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
13 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Saranga Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000144/2023-2024 | 2854/CMD | 05/07/2023 | 04/08/2023 | ORIENTAL ENGINEERING CO. | 28.97 | 22.55 | 77.83 | 100
14 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Material Requisition To Resource Division |  |  | RTOR000062/2024-2025 | 388/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 2.06 | 0 | 0 | 0
15 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Continuation for Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of SARANGA PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01.10.2025 to 31.12.2025]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000792/2025-2026 | 1270/DSD | 25/09/2025 | 03/01/2026 | ANWESHA CONSTRUCTION | 0.63 | 0 | 0 | 0
16 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Continuation work for Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of SARANGA PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01/01/2026 to 31/03/2026]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001101/2025-2026 | 1459/DSD | 30/12/2025 | 30/03/2026 | ANWESHA CONSTRUCTION | 0.63 | 0 | 0 | 0
17 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME | SM/14078 | New | Continuation work for Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of SARANGA PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01/04/2026 to 30/06/2026]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001119/2025-2026 | 221/DSD | 27/03/2026 | 26/06/2026 | ANWESHA CONSTRUCTION | 0.63 | 0 | 0 | 0
Total | [13 empty] | 1045.52 | 275.08 | 26.31