## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME | SM/14079 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 20.38 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME | SM/14079 | New | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 9.61 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | BARA KULGACHHI PIPED WATER SUPPLY SCHEME | SM/14079 | New | New service connection charges for Barakulgachi PWSS TW-2 |  |  | BILL/00882/2023-2024 | BP-2023-24-108 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.73 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | BARA KULGACHHI PIPED WATER SUPPLY SCHEME | SM/14079 | New | New service connection charges for Bara Kulgachi PWSS TW-1 |  |  | BILL/01353/2023-2024 | BP-2023-24-131 | 22/08/2023 | 22/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.92 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME | SM/14079 | New | BARA KULGACHHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000709/2022-2023 | 775/BWD | 24/02/2023 | 31/07/2026 | MANASH GHOSH | 557.58 | 0 | 0 | 73
6 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | BARA KULGACHHI PIPED WATER SUPPLY SCHEME | SM/14079 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000070/2024-2025 | 2409/CMD | 02/08/2024 | 31/10/2024 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Katwa-II | Central Mechanical | BARA KULGACHHI PIPED WATER SUPPLY SCHEME | SM/14079 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BARAKULGACHHI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000234/2023-2024 | 3173/CMD | 26/07/2023 | 25/08/2023 | GOENKA ENTERPRISE | 28.98 | 0 | 0 | 90
8 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME | SM/14079 | New | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | AE(HQs) | J.E. 1 BURDWAN | ORD/001212/2023-2024 | 907/BWD | 04/03/2024 | 03/04/2024 | MANASH GHOSH | 23.87 | 0 | 0 | 100
9 | PURBA BARDHAMAN | Katwa-II | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME | SM/14079 | New | Material Requisition To Resource Division |  |  | RTOR000792/2023-2024 | 331/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 16.79 | 0 | 0 | 0
Total | [13 empty] | 717.04 | 0 | 0