## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Material Requisition To Resource Division |  |  | RTOR000442/2023-2024 | 3834/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 5.48 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Material Requisition To Resource Division |  |  | RTOR000677/2023-2024 | 5052/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | New service connection charges for Malkita PWSS TW-1 |  |  | BILL/00837/2023-2024 | BP-2023-24-102 | 04/08/2023 | 04/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | New service connection charges for Malkita PWSS TW-2 |  |  | BILL/00838/2023-2024 | BP-2023-24-103 | 04/08/2023 | 04/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.25 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | MALKITA Single Village Scheme with sinking of Tube-well & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000054/2023-2024 | 1933/BWD | 24/04/2023 | 23/07/2023 | GHOSH CONSTRUCTION | 49.99 | 0 | 0 | 100
7 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | MALKITA Single Village Scheme with LDS, Rising Main and FHTC under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000158/2023-2024 | 2454/BWD | 31/05/2023 | 29/08/2023 | M/S PURBASHA | 71.78 | 0 | 0 | 72
8 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/01/2026 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
9 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Installation of Sluice Valve, Washout Valve to regulate water supply with Road Restoration work, Extension pipeline and providing FHTC for MALKITA Piped Water Supply Scheme, Block- Burdwan-I, under Burdwan sub Division within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001163/2024-2025 | 552/BWD | 04/02/2025 | 05/05/2025 | M/S PURBASHA | 9.62 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Malkita Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000211/2023-2024 | 3067/CMD | 21/07/2023 | 20/08/2023 | S.P. CONSTRUCTION | 28.96 | 0 | 0 | 100
Total | [13 empty] | 559.34 | 0 | 0