## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Material Requisition To Resource Division |  |  | RTOR000442/2023-2024 | 3834/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 5.48 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Material Requisition To Resource Division |  |  | RTOR000677/2023-2024 | 5052/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | New service connection charges for Malkita PWSS TW-1 |  |  | BILL/00837/2023-2024 | BP-2023-24-102 | 04/08/2023 | 04/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | New service connection charges for Malkita PWSS TW-2 |  |  | BILL/00838/2023-2024 | BP-2023-24-103 | 04/08/2023 | 04/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.25 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | MALKITA Single Village Scheme with sinking of Tube-well & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000054/2023-2024 | 1933/BWD | 24/04/2023 | 23/07/2023 | GHOSH CONSTRUCTION | 49.99 | 49.95 | 99.91 | 100
7 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | MALKITA Single Village Scheme with LDS, Rising Main and FHTC under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000158/2023-2024 | 2454/BWD | 31/05/2023 | 29/08/2023 | M/S PURBASHA | 71.78 | 71.76 | 99.98 | 72
8 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Installation of Sluice Valve, Washout Valve to regulate water supply with Road Restoration work, Extension pipeline and providing FHTC for MALKITA Piped Water Supply Scheme, Block- Burdwan-I, under Burdwan sub Division within Burdwan Division PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001163/2024-2025 | 552/BWD | 04/02/2025 | 05/05/2025 | M/S PURBASHA | 9.62 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14080 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Malkita Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000211/2023-2024 | 3067/CMD | 21/07/2023 | 20/08/2023 | S.P. CONSTRUCTION | 28.96 | 21.66 | 74.79 | 100
Total | [13 empty] | 249.74 | 143.37 | 57.41