## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-I,Ausgram-II,Bhatar,Burdwan-I,Galsi-I,Galsi-II,Kalna-I,Kalna-II,Katwa-I,Katwa-II,Ketugram-I,Ketugram-II,Khandaghosh,Mangolkote,Manteswar,Memari-II,Purbasthali-I,Raina-I,Raina-II | Burdwan Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/14132 | New | Implementation of Ground Water Based Mini Piped Water supply Scheme in 129 Nos. villages in Aushgram I & II, Burdwan I & II, Galsi I & II, Katwa I & II, Ketugream I & II, Raina I & II, Bhatar, Khandaghosh, Mongalkote and Memari II Block maximum 100 households in Purba Bardhaman district under Burdwan Division, PHE. Dte. | Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000703/2022-2023 | 641/BWD | 20/02/2023 | 28/12/2025 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4231.72 | 1214.93 | 28.71 | 42
2 | PURBA BARDHAMAN | Ausgram-I,Ausgram-II,Bhatar,Burdwan-I,Galsi-I,Galsi-II,Kalna-I,Kalna-II,Katwa-I,Katwa-II,Ketugram-I,Ketugram-II,Khandaghosh,Mangolkote,Manteswar,Memari-II,Purbasthali-I,Raina-I,Raina-II | Central Mechanical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/14132 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 6 at Augmentation of Bhatar (Zone - II) (Bhumsor) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000933/2022-2023 | 1310/CMD | 22/03/2023 | 21/04/2023 | SUDIPTA GHOSH | 12.05 | 11.62 | 96.4 | 95
3 | PURBA BARDHAMAN | Ausgram-I,Ausgram-II,Bhatar,Burdwan-I,Galsi-I,Galsi-II,Kalna-I,Kalna-II,Katwa-I,Katwa-II,Ketugram-I,Ketugram-II,Khandaghosh,Mangolkote,Manteswar,Memari-II,Purbasthali-I,Raina-I,Raina-II | Burdwan Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/14132 | New | Conducting physical Household Survey at the IMIS reported village for HGJ certification and providing balance FHTC for Har Ghar Jal certification including conducting Gram Sabhas for different IMIS reported villages across the district under Burdwan Division, PHE Dte. | AE(HQs),Assistant Engineer ,Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000428/2024-2025 | 3107/BWD | 12/08/2024 | 01/04/2026 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 309.6 | 0 | 0 | 85
4 | PURBA BARDHAMAN | Ausgram-I,Ausgram-II,Bhatar,Burdwan-I,Galsi-I,Galsi-II,Kalna-I,Kalna-II,Katwa-I,Katwa-II,Ketugram-I,Ketugram-II,Khandaghosh,Mangolkote,Manteswar,Memari-II,Purbasthali-I,Raina-I,Raina-II | Central Mechanical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/14132 | New | Quotation for new service connection at Nabagram PWSS TW-3 |  |  | BILL/00960/2024-2025 | BP-2024-25-381 | 14/11/2024 | 14/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 19.77 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-I,Ausgram-II,Bhatar,Burdwan-I,Galsi-I,Galsi-II,Kalna-I,Kalna-II,Katwa-I,Katwa-II,Ketugram-I,Ketugram-II,Khandaghosh,Mangolkote,Manteswar,Memari-II,Purbasthali-I,Raina-I,Raina-II | Central Mechanical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/14132 | New | Quotation for new service connection at Jahannagar Augmentation PWSS TW-3 |  |  | BILL/01036/2024-2025 | BP-2024-25-382 | 14/11/2024 | 14/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.54 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-I,Ausgram-II,Bhatar,Burdwan-I,Galsi-I,Galsi-II,Kalna-I,Kalna-II,Katwa-I,Katwa-II,Ketugram-I,Ketugram-II,Khandaghosh,Mangolkote,Manteswar,Memari-II,Purbasthali-I,Raina-I,Raina-II | Burdwan Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE | SM/14132 | New | Designing, making and erection of Sign Board for SWAJAL GRAM in Jamaipota village of Raina-I Block under Mini Piped Water Supply Scheme (100 Household) within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos. Board) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000477/2025-2026 | 2341/BSD | 21/08/2025 | 31/08/2025 | S.M. ENGOCON | 0.72 | 0 | 0 | 0
Total | [13 empty] | 4581.4 | 1226.54 | 26.77