## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khule Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000923/2023-2024 | 4186/CMD | 29/08/2023 | 28/09/2023 | CINZANO | 29.1 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 56.68 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | Material Requisition To Resource Division |  |  | RTOR000180/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 18.09 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR ANUKHAL PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000962/2024-2025 | 1236/KSD | 30/09/2024 | 15/10/2024 | SINGHA ROY AND CO. | 0.66 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | Work order for " CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DOGACHHIA PWSS UNDER KALNA SUBDIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000963/2024-2025 | 1237/KSD | 30/09/2024 | 15/10/2024 | MITRA CONSTRUCTION | 0.66 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | NEW SERVICE CONNECTION FOR KHULE PWSS. |  |  | BILL/02696/2023-2024 | BP-2023-24-569 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.69 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | NEW SERVICE CONNECTION FOR KHULE PWSS. |  |  | BILL/02697/2023-2024 | BP-2023-24-570 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.79 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | KHULE Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000004/2023-2024 | 1618/BWD | 05/04/2023 | 04/04/2024 | AZAD ENTERPRISE | 598.72 | 0 | 0 | 55
9 | PURBA BARDHAMAN | Manteswar | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2025 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
10 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Manteswar | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte | SM/14425 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR KHULE PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE.". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001289/2024-2025 | 1232/KSD | 27/09/2024 | 12/10/2024 | WESTON ENGINEERS | 0.66 | 0 | 0 | 100
Total | [13 empty] | 1483.41 | 0 | 0