## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 1640/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 4.7 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Material Requisition To Resource Division |  |  | RTOR000087/2022-2023 | 1237/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 10.42 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Material Requisition To Resource Division |  |  | RTOR000515/2023-2024 | 3967/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 19.84 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Material Requisition To Resource Division |  |  | RTOR000638/2023-2024 | 5093/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 21.42 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | New service connection charges for Deara PWSS TW-1 |  |  | BILL/01669/2023-2024 | BP-2023-24-222 | 10/11/2023 | 10/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.46 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 31/10/2024 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Work Order for "Supply of 1 (one) No. Diesel driven Motor cab (Inspection vehicle) on hire basis for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period for 3 (Three) Months]". | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000668/2023-2024 | 1333/KSD | 28/08/2023 | 08/11/2023 | PARTHA PRATIM ACHARYA | 0.92 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Work order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DEARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001143/2023-2024 | 1979/KSD | 09/02/2024 | 19/02/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0 | 0 | 100
9 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | New service connection for DEARA PWSS |  |  | BILL/02561/2023-2024 | BP-2023-24-544 | 19/02/2024 | 19/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.53 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEARA, PATHARDANGA & SHIKARPUR Piped Water Supply Scheme under KALNA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000734/2022-2023 | 1004/BWD | 06/03/2023 | 06/12/2024 | M/S TAPAS KUMAR CHAKRABORTY | 1584.09 | 0 | 0 | 75
11 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 07/02/2026 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
12 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Deara Water Supply Scheme [ Block- KALNA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000757/2023-2024 | 4060/CMD | 29/08/2023 | 26/12/2024 | S.K. ENTERPRISE | 28.6 | 0 | 0 | 100
13 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Installation of Electrical items & allied works for Urgent FHTC for Deara PH 1 water supply scheme under CMD P.H.E. Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000500/2024-2025 | 822/CMSD | 31/05/2024 | 30/06/2024 | S.K. ENTERPRISE | 0.64 | 0 | 0 | 100
14 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME | SM/14435 | New | Continuation Order-Providing Diesel generator set at DEARA Water supply scheme for Urgent FHTC connection under CMD PHE Dte. [W.E.F- 05.06.2024 TO 08.06.2024] | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000461/2024-2025 | 827/CMSD | 04/06/2024 | 11/06/2024 | S.K. ENTERPRISE | 0.85 | 0 | 0 | 100
Total | [13 empty] | 2949.19 | 0 | 0