## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 1249/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 15.17 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 41.55 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Quotation for new electric service connection at Shikarpur PH NO.-2 |  |  | BILL/01736/2023-2024 | BP-2023-24-247 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.73 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 31/10/2024 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Work Order For "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR NANDAI PWSS & SHIKARPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001144/2023-2024 | 1980/KSD | 09/02/2024 | 19/02/2024 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.33 | 49.89 | 100
6 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Electric quotation for New Service Connection at Shikarpur W/S Scehem PH-I. |  |  | BILL/01774/2023-2024 | BP-2023-24-287 | 26/12/2023 | 26/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.57 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEARA, PATHARDANGA & SHIKARPUR Piped Water Supply Scheme under KALNA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000734/2022-2023 | 1004/BWD | 06/03/2023 | 06/12/2024 | M/S TAPAS KUMAR CHAKRABORTY | 1584.09 | 319.18 | 20.15 | 75
8 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Temporary approach road from Shikarpur Graveyard to OHr site and Shikarpur Bus stand to 2nd tube well site in order to carry building materials for Shikarpur Piped W/S. Scheme (SM/14437) within Kalna Sub-Division under Burdwan Division, PHE. Dte. | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001229/2024-2025 | 767/BWD | 27/02/2025 | 14/03/2025 | M/S TAPAS KUMAR CHAKRABORTY | 5.75 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer |  | ORD/001270/2024-2025 | 849/BWD | 05/03/2025 | 01/09/2025 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 07/02/2026 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
11 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SHIKARPUR Water Supply Scheme [ Block- KALNA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000836/2023-2024 | 4110/CMD | 29/08/2023 | 28/09/2023 | CHOUDHURY ENTERPRISE | 30.14 | 12.16 | 40.34 | 50
12 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME | SM/14437 | New | Work Order for " Restoration of pipeline with other allied works at different places of Shikarpur mouja under Shikarpur Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000526/2024-2025 | 969/KSD | 31/07/2024 | 10/08/2024 | M/S TAPAS KUMAR CHAKRABORTY | 3.58 | 0 | 0 | 100
Total | [13 empty] | 3642.59 | 331.67 | 9.11