## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Material Requisition To Resource Division |  |  | RTOR000319/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 12.94 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Material Requisition To Resource Division |  |  | RTOR000455/2023-2024 | 3979/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 32.04 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Providing FHTC with laying of 90 mm dia HDPE Pipe of Susunia PWSS of Kuli village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte |  |  | ORD/001163/2023-2024 | 269/DSD | 15/03/2024 | 14/04/2024 | SOUMYAVASH DAS | 0.94 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Construction of valve chamber HD works site and installation of sluice valve at Budpur village of Susunia PWSS under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte |  |  | ORD/001164/2023-2024 | 268./DSD | 15/03/2024 | 14/04/2024 | PRONAB KUMAR DEY | 0.94 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Providing FHTC with laying of 90 mm dia HDPE Pipe of Susunia PWSS under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte |  |  | ORD/001161/2023-2024 | 266/DSD | 15/03/2024 | 14/04/2024 | PRONAB KUMAR DEY | 0.95 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Manteswar | Central Mechanical | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Shushna Water Supply Scheme [ Block- MONTESWAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000761/2023-2024 | 4062/CMD | 29/08/2023 | 28/09/2023 | ORIENTAL ENGINEERING CO. | 28.97 | 23.46 | 80.97 | 80
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | New service at Shushna PWSS TW-2. |  |  | BILL/02291/2023-2024 | BP-2023-24-440 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.03 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Manteswar | Central Mechanical | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | New Service connection at SHUSHNA PWSS TW-1. |  |  | BILL/02359/2023-2024 | BP-2023-24-481 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.48 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PASCHIM KHARAMPUR, SHUSHNA & SIGHNALI Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000482/2023-2024 | 3494/BWD | 09/08/2023 | 30/09/2025 | S.P. CONSTRUCTION | 1925.07 | 305.44 | 15.87 | 80
10 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Providing FHTC with laying of 90 mm dia HDPE Pipe of Susunia PWSS of kalsar village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte |  | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001162/2023-2024 | 267./DSD | 15/03/2024 | 01/04/2025 | PRONAB KUMAR DEY | 0.97 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Manteswar | Central Mechanical | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000590/2024-2025 | 3105/CMD | 11/12/2024 | 09/02/2025 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Manteswar | Central Mechanical | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2025 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
13 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Continuation for Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of SHUSHNA PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01.10.2025 to 31.12.2025]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000793/2025-2026 | 1271/DSD | 25/09/2025 | 03/01/2026 | A.R. TRADERS | 0.63 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Continuation for Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of SHUSHNA PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01/04/2026 TO 30/06/2026]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001129/2025-2026 | 230/DSD | 27/03/2026 | 26/06/2026 | A.R. TRADERS | 0.63 | 0 | 0 | 0
15 | PURBA BARDHAMAN | Manteswar | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME | SM/14438 | New | Continuation for Operation of Distribution System , Rising main, Sluice Valves, including operation of sluice valves of SHUSHNA PWSS within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Period for 01/01/2026 TO 31/03/2026]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001110/2025-2026 | 1468/DSD | 30/12/2025 | 30/03/2026 | A.R. TRADERS | 0.63 | 0 | 0 | 0
Total | [13 empty] | 2113.05 | 328.9 | 15.57