## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEARA, PATHARDANGA & SHIKARPUR Piped Water Supply Scheme under KALNA-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000734/2022-2023 | 1004/BWD | 06/03/2023 | 06/12/2024 | M/S TAPAS KUMAR CHAKRABORTY | 1584.09 | 483.06 | 30.49 | 75
2 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PATHARDANGA Water Supply Scheme [ Block- KALNA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000690/2023-2024 | 4016/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 29.61 | 11.65 | 39.33 | 60
3 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Work Order for Supply of 1 (one) No. Diesel driven Motor cab on hire basis for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2023 to 31.12.2023] |  |  | ORD/000898/2023-2024 | 825/KSD | 28/06/2023 | 29/12/2023 | PARTHA PRATIM ACHARYA | 0 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Material Requisition To Resource Division |  |  | RTOR000103/2022-2023 | 1636/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 4.2 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Material Requisition To Resource Division |  |  | RTOR000088/2022-2023 | 1242/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 17.57 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Material Requisition To Resource Division |  |  | RTOR000498/2023-2024 | 4022/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 34.67 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | New service connection charges for Pathardanga PWSS TW-2 |  |  | BILL/01530/2023-2024 | BP-2023-24-198 | 13/10/2023 | 13/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.06 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | New Service connection for Pathardanga W/S Scheme PH No.-1 |  |  | BILL/01803/2023-2024 | BP-2023-24-307 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.44 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 31/10/2024 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Work order for "Restoration of pipeline with other allied works at different places of Ghanashyampur mouja under Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000861/2024-2025 | 1846/KSD | 27/11/2024 | 12/12/2024 | M/S TAPAS KUMAR CHAKRABORTY | 4.22 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Work order for " Restoration of pipeline with other allied works at different places of Pathardanga mouja under Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000862/2024-2025 | 1847/KSD | 27/11/2024 | 12/12/2024 | M/S TAPAS KUMAR CHAKRABORTY | 4.14 | 0 | 0 | 100
12 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Work order for "Restoration of pipeline with other allied works at different places of Beshbati mouja of Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000867/2024-2025 | 1852/KSD | 27/11/2024 | 12/12/2024 | M/S TAPAS KUMAR CHAKRABORTY | 3.58 | 0 | 0 | 100
13 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Work order for "Restoration of pipeline with other allied works at different places of Rampur mouja under Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000864/2024-2025 | 1849/KSD | 27/11/2024 | 12/12/2024 | M/S TAPAS KUMAR CHAKRABORTY | 3.66 | 0 | 0 | 100
14 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL UNDER PATHARDANGA PWSS AND TAIPARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE. (2 UNITS:- 1 NO FOR PATHARDANGA PWSS & 1 NO FOR TAIPARA PWSS)" | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001141/2023-2024 | 1977/KSD | 09/02/2024 | 19/02/2024 | BISWAS ENTERPRISE | 0.66 | 0.33 | 49.89 | 100
15 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Work Order for "Restoration of pipeline with other allied works at different places of Indrapur mouja under Patahrdanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000523/2024-2025 | 966/KSD | 31/07/2024 | 10/08/2024 | M/S TAPAS KUMAR CHAKRABORTY | 3.12 | 0 | 0 | 100
16 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Work Order for "Restoration of pipeline with other allied works at different places of parshapur mouja under Patahrdanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000524/2024-2025 | 967/KSD | 31/07/2024 | 10/08/2024 | M/S TAPAS KUMAR CHAKRABORTY | 2.21 | 1.35 | 60.99 | 100
17 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME | SM/14440 | New | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/001187/2024-2025 | 608/BWD | 11/02/2025 | 07/02/2026 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
Total | [13 empty] | 2965.31 | 496.39 | 16.74