## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Material Requisition To Resource Division |  |  | RTOR000183/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 14.82 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Material Requisition To Resource Division |  |  | RTOR000628/2023-2024 | 4888/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 29.45 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 22.25 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Quotation for New Electric Connection for Taipara W/S Scheme PH NO.-1 |  |  | BILL/01733/2023-2024 | BP-2023-24-248 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.1 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Electric quotation for New Service Connection at Taipara W/S Scehem PH-2. |  |  | BILL/01776/2023-2024 | BP-2023-24-288 | 26/12/2023 | 26/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.67 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 31/10/2024 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Work Order for "Restoration of pipeline with other allied works at different places of Dhaleswar mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000548/2024-2025 | 973/KSD | 31/07/2024 | 10/08/2024 | S.GHOSH & ASSOCIATES PVT LTD. | 2.29 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL UNDER PATHARDANGA PWSS AND TAIPARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE. (2 UNITS:- 1 NO FOR PATHARDANGA PWSS & 1 NO FOR TAIPARA PWSS)" | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/001141/2023-2024 | 1977/KSD | 09/02/2024 | 19/02/2024 | BISWAS ENTERPRISE | 0.66 | 0 | 0 | 100
9 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Work order for "Restoration of pipeline with other allied works at different places of Bagpur mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000528/2024-2025 | 971/KSD | 31/07/2024 | 10/08/2024 | S.GHOSH & ASSOCIATES PVT LTD. | 2.84 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Work order for "Restoration of pipeline with other allied works at different places of Rajkhara mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000527/2024-2025 | 970/KSD | 31/07/2024 | 10/08/2024 | S.GHOSH & ASSOCIATES PVT LTD. | 2.75 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Work Order for "Restoration of pipeline with other allied works at different places of Bherua mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000529/2024-2025 | 972/KSD | 31/07/2024 | 10/08/2024 | S.GHOSH & ASSOCIATES PVT LTD. | 3.39 | 0 | 0 | 100
12 | PURBA BARDHAMAN | Kalna-I | Burdwan Division | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to TAIPARA & NIRALGACHHI Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | Junior Engineer, R.W.S. Burdwan Sub Division, P.H.E. Dt | ORD/000048/2023-2024 | 1825/BWD | 19/04/2023 | 31/08/2025 | S. GHOSH & ASSOCIATES PVT LTD. | 1064.74 | 0 | 0 | 85
13 | PURBA BARDHAMAN | Kalna-I | Central Mechanical | TAIPARA Piped Water Supply Scheme. | SM/14442 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Taipara Water Supply Scheme [ Block- KALNA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000762/2023-2024 | 4063/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 28.89 | 0 | 0 | 90
Total | [13 empty] | 1238.27 | 0 | 0