## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000420/2023-2024 | 593/DSD | 31/07/2023 | 05/10/2023 | AFIBS ENTERPRISE | 0.85 | 0 | 0 | 100
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 27.18 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | Material Requisition To Resource Division |  |  | RTOR000176/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 17.06 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | Material Requisition To Resource Division |  |  | RTOR000583/2023-2024 | 4897/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 38.94 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | New service connection charges for Nasigram PWSS TW-1 |  |  | BILL/00772/2023-2024 | BP-2023-24-72 | 21/07/2023 | 21/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.83 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | New service connection charges for Nasigram PWSS TW-2 |  |  | BILL/00773/2023-2024 | BP-2023-24-73 | 21/07/2023 | 21/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | Continuation Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/11/2023 to 31/01/2024] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/001210/2023-2024 | 825/DSD | 31/10/2023 | 05/01/2024 | AFIBS ENTERPRISE | 0.85 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | Making connection with 4th tube well, Construction of Plinth protection of OHR, Restoration of road and FHTC (The rest portion) of Bara Belun Water Supply Scheme at Bara Belun village & Providing Functional Household Tap Connection (FHTC) within the command area of NASIGRAM Piped W/S. Scheme within Bhatar Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000690/2024-2025 | 3685/BWD | 23/10/2024 | 20/02/2025 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 91.48 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Bhatar | Central Mechanical | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | Continuation Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/11/2023 to 31/01/2024] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000755/2023-2024 | 825/DSD | 31/10/2023 | 05/01/2024 | AFIBS ENTERPRISE | 0.85 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Bhatar | Central Mechanical | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | NEW SERVICE CONNECTION FOR NASIGRAM PWSS |  |  | BILL/02592/2023-2024 | BP-2023-24-574 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.54 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Bhatar | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | NASIGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000050/2023-2024 | 1826/BWD | 19/04/2023 | 30/04/2025 | MD HASIN | 742.95 | 0 | 0 | 50
13 | PURBA BARDHAMAN | Bhatar | Central Mechanical | NASIGRAM PIPED WATER SUPPLY SCHEME | SM/14443 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at NASIGRAM Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000141/2023-2024 | 2856/CMD | 05/07/2023 | 04/08/2023 | M/S. S.R. ENTERPRISE | 41.65 | 0 | 0 | 90
Total | [13 empty] | 1058.34 | 0 | 0