## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Manteswar | Burdwan Division | IBRAMBAD PIPED WATER SUPPLY SCHEME | SM/14444 | New | Material Requisition To Resource Division |  |  | RTOR000278/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 3.02 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Manteswar | Burdwan Division | IBRAMBAD PIPED WATER SUPPLY SCHEME | SM/14444 | New | Material Requisition To Resource Division |  |  | RTOR000520/2023-2024 | 4052/BWD | 11/09/2023 | 11/09/2023 | Resource Division | 3.03 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Manteswar | Burdwan Division | IBRAMBAD PIPED WATER SUPPLY SCHEME | SM/14444 | New | Material Requisition To Resource Division |  |  | RTOR000454/2023-2024 | 3978/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 32.08 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Manteswar | Burdwan Division | IBRAMBAD PIPED WATER SUPPLY SCHEME | SM/14444 | New | Material Requisition To Resource Division |  |  | RTOR000780/2023-2024 | 323/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 34.15 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Manteswar | Central Mechanical | IBRAMBAD PIPED WATER SUPPLY SCHEME | SM/14444 | New | Quotation for new electric service connection at Ibrambad PH NO.-2 |  |  | BILL/01749/2023-2024 | BP-2023-24-249 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.13 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Manteswar | Central Mechanical | IBRAMBAD PIPED WATER SUPPLY SCHEME | SM/14444 | New | NEW SERVICE CONNECTION FOR IBRAMBAD PWSS. |  |  | BILL/02690/2023-2024 | BP-2023-24-573 | 27/02/2024 | 27/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.51 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Manteswar | Central Mechanical | IBRAMBAD PIPED WATER SUPPLY SCHEME | SM/14444 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000068/2024-2025 | 2396/CMD | 02/08/2024 | 31/10/2025 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
8 | PURBA BARDHAMAN | Manteswar | Central Mechanical | IBRAMBAD PIPED WATER SUPPLY SCHEME | SM/14444 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Ibrambad Water Supply Scheme [ Block- Monteswar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000765/2023-2024 | 4064/CMD | 29/08/2023 | 28/09/2023 | M/S. S.R. ENTERPRISE | 28.96 | 22.76 | 78.59 | 90
Total | [13 empty] | 189.93 | 22.76 | 11.98