## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | SM/14445 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GOBARDHANPUR Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | Driller In-Charge | Junior Engineer | ORD/000933/2023-2024 | 4196/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 29.71 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | SM/14445 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 1965/BWD | 26/04/2023 | 26/04/2023 | Resource Division | 17.79 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | SM/14445 | New | Material Requisition To Resource Division |  |  | RTOR000385/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 13.53 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | SM/14445 | New | Material Requisition To Resource Division |  |  | RTOR000714/2023-2024 | 5277/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.37 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | SM/14445 | New | Quotation for new service connection at Gobardhanpur PWSS TW-1 |  |  | BILL/01087/2024-2025 | BP-2024-25-397 | 22/11/2024 | 22/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | SM/14445 | New | Quotation for new service connection for Gobardhanpur PWSS TW-2. |  |  | BILL/00252/2024-2025 | BP-2024-25-131 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.11 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | SM/14445 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000477/2023-2024 | 3491/BWD | 09/08/2023 | 02/07/2026 | POWER TOOLS & ENGINEERING | 1741.05 | 0 | 0 | 10
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | SM/14445 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
9 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | SM/14445 | New | Designing, making and erection of Sign Board for SWAJAL GRAM in Taharpur village of Memari-I Block under Gobindapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte(5 nos Board) |  |  | ORD/000508/2025-2026 | 2352/BSD | 21/08/2025 | 31/08/2025 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | GOBARDHANPUR PIPED WATER SUPPLY SCHEME | SM/14445 | New | Suplimentary Qtn for addl,work of Gobardhanpur PWSS, TW 2 |  |  | BILL/02343/2025-2026 |  | 10/12/2025 | 10/12/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.63 | 0 | 0 | 0
Total | [13 empty] | 1892.5 | 0 | 0