## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME | SM/14448 | New | PURBA GOPALPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under MANGLAKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000020/2023-2024 | 1751/BWD | 13/04/2023 | 01/08/2025 | BRAHMA CONSTRUCTION COMPANY | 429.79 | 119.45 | 27.79 | 30
2 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME | SM/14448 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PURBA GOPALPUR Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000560/2023-2024 | 3873/CMD | 17/08/2023 | 14/08/2024 | UNIVERSAL ENTERPRISES | 29.94 | 24.24 | 80.97 | 90
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME | SM/14448 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 1965/BWD | 26/04/2023 | 26/04/2023 | Resource Division | 35.89 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME | SM/14448 | New | Material Requisition To Resource Division |  |  | RTOR000181/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 17.8 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME | SM/14448 | New | Material Requisition To Resource Division |  |  | RTOR000729/2023-2024 | 5263/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 20.78 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME | SM/14448 | New | New service connection charges for Purba Gopalpur PWSS TW-1 |  |  | BILL/01416/2023-2024 | BP-2023-24-144 | 31/08/2023 | 31/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.2 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME | SM/14448 | New | New service connection charges for Purba Gopalpur PWSS TW-2 |  |  | BILL/01769/2023-2024 | BP-2023-24-274 | 21/12/2023 | 21/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.51 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME | SM/14448 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME | SM/14448 | New | Constn. of pump house, Plinth Protection for Pump House & OHR, extension of pipeline for providing FHTC at MURULIA village, Adivasi para, approach road for 2nd Pump house of PURBA GOPALPUR PWSS Under Katwa Sub Division, Block- Mongolkote, Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/001124/2024-2025 | 496/BWD | 28/01/2025 | 01/03/2026 | MONDAL ENTERPRISE | 26.97 | 0 | 0 | 67
Total | [13 empty] | 630.93 | 143.69 | 22.77