## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Material Requisition To Resource Division |  |  | RTOR000330/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 10.1 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Material Requisition To Resource Division |  |  | RTOR000470/2023-2024 | 3994/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 12.51 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Material Requisition To Resource Division |  |  | RTOR000696/2023-2024 | 5059/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-I | Central Mechanical | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | New service connection charges for Tatarpur PWSS TW-1 |  |  | BILL/01761/2023-2024 | BP-2023-24-271 | 15/12/2023 | 15/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 38.7 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Memari-I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 29/05/2024 | SK.ASFIA | 2.4 | 0.4 | 16.59 | 70
6 | PURBA BARDHAMAN | Memari-I | Central Mechanical | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | New Service connection for Tatarpur W/S Scheme PH No.-II |  |  | BILL/01792/2023-2024 | BP-2023-24-309 | 30/12/2023 | 30/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.61 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | TATARPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000375/2023-2024 | 2621/BWD | 06/06/2023 | 01/01/2026 | RANADHIR SINHA | 359.46 | 154.5 | 42.98 | 50
8 | PURBA BARDHAMAN | Memari-I | Central Mechanical | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Tatarpur Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000466/2023-2024 | 3723/CMD | 08/08/2023 | 07/09/2023 | M.S. ENTERPRISE | 30.11 | 0 | 0 | 95
9 | PURBA BARDHAMAN | Memari-I | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME | SM/14740 | New | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for TATARPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/001116/2024-2025 | 479/BWD | 24/01/2025 | 24/04/2025 | RANADHIR SINHA | 74.75 | 0 | 0 | 0
Total | [13 empty] | 558.09 | 154.9 | 27.75