## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14906 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 4.69 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14906 | New | Material Requisition To Resource Division |  |  | RTOR000272/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 4.03 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14906 | New | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. | AE(HQs) | J.E. 1 BURDWAN | ORD/000756/2023-2024 | 842/AE/HQ | 01/11/2023 | 16/11/2023 | M/S S. CHOUDHURY | 0.33 | 0 | 0 | 100
4 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14906 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000066/2024-2025 | 2388/CMD | 02/08/2024 | 31/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14906 | New | Material Requisition To Resource Division |  |  | RTOR000790/2023-2024 | 332/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 21.17 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14906 | New | New service connection for HALDI PWSS TW 1. |  |  | BILL/02444/2023-2024 | BP-2023-24-523 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Burdwan-I | Central Mechanical | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14906 | New | NEW SERVICE CONNECTION FOR HALDI PWSS |  |  | BILL/02835/2023-2024 | BP-2023-24-591 | 04/03/2024 | 04/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.5 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14906 | New | Continuation for the work of Supply of one No. Diesel Driven Car ( other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub- Division, PHE Dte. (Period from 01-07-2025 to 31-08-2025). | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Contractual Junior Engineer | ORD/000168/2025-2026 | 158/RWS | 30/06/2025 | 31/08/2025 | MD HASIN | 0.8 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Burdwan-I | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME | SM/14906 | New | Continuation for the work of Supply of one No. Diesel Driven Car ( other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub- Division, PHE Dte. (Period from 01-09-2025 to 31-10-2025). | ASSISTANT ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | Contractual Junior Engineer | ORD/000598/2025-2026 | 197/RWS | 01/09/2025 | 01/11/2025 | MD HASIN | 0.8 | 0 | 0 | 0
Total | [13 empty] | 101.26 | 0 | 0