## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 6.74 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | Material Requisition To Resource Division |  |  | RTOR000270/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 7.32 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | Material Requisition To Resource Division |  |  | RTOR000557/2023-2024 | 4890/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 10.17 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | Quotation for new service connection for Ramchandrapur Zone-2 PWSS PH 1. |  |  | BILL/00226/2024-2025 | BP-2024-25-117 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.39 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | NEW SERVICE CONNECTION FOR RAMCHANDRAPUR ZONE - I PWSS |  |  | BILL/02593/2023-2024 | BP-2023-24-551 | 20/02/2024 | 20/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.15 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | Quotation for new service connection for Ramchandarapur Zone-2 PWSS PH 2. |  |  | BILL/00227/2024-2025 | BP-2024-25-118 | 29/05/2024 | 29/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.35 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Bhatar | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | Quotation for new service connection at Ramchandrapur Zone-1 PWSS PH-2 |  |  | BILL/00392/2024-2025 | BP-2024-25-205 | 18/07/2024 | 18/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.44 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Bhatar | Burdwan Division | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | RAMCHANDRAPUR (ZONE-I & II ) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000536/2023-2024 | 3703/BWD | 24/08/2023 | 01/07/2025 | SUPRITI ENTERPRISE | 582.13 | 0 | 0 | 60
10 | PURBA BARDHAMAN | Bhatar | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2, 3 & 4 at RAMCHANDRAPUR Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000919/2023-2024 | 4183/CMD | 29/08/2023 | 28/09/2023 | M/S, S.S. ENTERPRISE. | 56.97 | 30.58 | 53.68 | 40
11 | PURBA BARDHAMAN | Bhatar | Burdwan Division | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | Material Requisition To Resource Division |  |  | RTOR000083/2024-2025 | 409/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 2.94 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Bhatar | Burdwan Division | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14909 | New | Diversion of some portion of Ramchandrapur 11 KV feeder from the premises of PHE Dauradanga Pump House emanating from Orgram 33/11 Sub-Station under Burdwan North Division. |  |  | BILL/00325/2025-2026 |  | 12/06/2025 | 12/06/2025 | WBSEDCL | 3.34 | 0 | 0 | 0
Total | [13 empty] | 771.93 | 30.58 | 3.96