## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NIGAN PIPE WATER SUPPLY SCHEME | SM/14912 | New | NIGAN Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 250 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000142/2023-2024 | 2386/BWD | 23/05/2023 | 22/05/2024 | AKASH CONSTRUCTION | 400.98 | 27.53 | 6.87 | 15
2 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NIGAN PIPE WATER SUPPLY SCHEME | SM/14912 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nigan Water Supply Scheme [ Block- MONGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000770/2023-2024 | 4068/CMD | 29/08/2023 | 08/08/2025 | AHALYA ENGINEERING WORKS | 27.78 | 0 | 0 | 44
3 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NIGAN PIPE WATER SUPPLY SCHEME | SM/14912 | New | Material Requisition To Resource Division |  |  | RTOR000356/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 10.74 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NIGAN PIPE WATER SUPPLY SCHEME | SM/14912 | New | Material Requisition To Resource Division |  |  | RTOR000459/2023-2024 | 3983/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 3.91 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NIGAN PIPE WATER SUPPLY SCHEME | SM/14912 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
6 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NIGAN PIPE WATER SUPPLY SCHEME | SM/14912 | New | Material Requisition To Resource Division |  |  | RTOR000806/2023-2024 | 303/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 20.47 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NIGAN PIPE WATER SUPPLY SCHEME | SM/14912 | New | Quotation for new service connection at Nigan PWSS TW-1 |  |  | BILL/01084/2024-2025 | BP-2024-25-394 | 22/11/2024 | 22/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.95 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | NIGAN PIPE WATER SUPPLY SCHEME | SM/14912 | New | Quotation for new service connection at Nigan PWSS TW-2 |  |  | BILL/01085/2024-2025 | BP-2024-25-395 | 22/11/2024 | 22/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.15 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | NIGAN PIPE WATER SUPPLY SCHEME | SM/14912 | New | Material Requisition To Resource Division |  |  | RTOR000076/2024-2025 | 402/BWD | 17/01/2025 | 17/01/2025 | Resource Division | 0.88 | 0 | 0 | 0
Total | [13 empty] | 536.51 | 27.53 | 5.13