## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KUNDA PIPED WATER SUPPLY SCHEME | SM/14913 | New | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 1965/BWD | 26/04/2023 | 26/04/2023 | Resource Division | 1.64 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KUNDA PIPED WATER SUPPLY SCHEME | SM/14913 | New | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 12.34 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KUNDA PIPED WATER SUPPLY SCHEME | SM/14913 | New | New service connection charges of Kunda W/S Scheme TW-1 |  |  | BILL/00689/2023-2024 | BP-2023-24-34 | 26/06/2023 | 26/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.56 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KUNDA PIPED WATER SUPPLY SCHEME | SM/14913 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KUNDA Water Supply Scheme [Block - MANGALKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000056/2023-2024 | 2518/CMD | 02/06/2023 | 02/07/2023 | M/S. S.R. ENTERPRISE | 21.04 | 0 | 0 | 40
5 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | KUNDA PIPED WATER SUPPLY SCHEME | SM/14913 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KUNDA PIPED WATER SUPPLY SCHEME | SM/14913 | New | KUNDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at Brahmapur, Jartha village (J.L No -76, 75) under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000775/2022-2023 | 1341/BWD | 22/03/2023 | 20/06/2023 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 57.05 | 0 | 0 | 60
7 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KUNDA PIPED WATER SUPPLY SCHEME | SM/14913 | New | KUNDA Piped Water Supply Scheme with balance LDS and FHTC at Kunda village, J.L No- 74 under Mongolkote Block, District:- Purba-Bardhaman. [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000095/2023-2024 | 2232/BWD | 16/05/2023 | 14/08/2023 | ASMA ENTERPRISE | 32.47 | 0 | 0 | 35
8 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | KUNDA PIPED WATER SUPPLY SCHEME | SM/14913 | New | Material Requisition To Resource Division |  |  | RTOR000813/2023-2024 | 302/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 14.25 | 0 | 0 | 0
Total | [13 empty] | 203.42 | 0 | 0