## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | SHRIGRAM PIPED WATER SUPPLY SCHEME | SM/14915 | New | Material Requisition To Resource Division |  |  | RTOR000312/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 12.32 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | SHRIGRAM PIPED WATER SUPPLY SCHEME | SM/14915 | New | Material Requisition To Resource Division |  |  | RTOR000486/2023-2024 | 4010/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 0.28 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | SHRIGRAM PIPED WATER SUPPLY SCHEME | SM/14915 | New | Material Requisition To Resource Division |  |  | RTOR000760/2023-2024 | 5245/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 18.9 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-I | Burdwan Division | SHRIGRAM PIPED WATER SUPPLY SCHEME | SM/14915 | New | SHRIGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -I Block, District:- Purba- Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000141/2023-2024 | 2385/BWD | 23/05/2023 | 22/05/2024 | S.D. CONSTRUCTION | 351.47 | 129.4 | 36.82 | 43
5 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | SHRIGRAM PIPED WATER SUPPLY SCHEME | SM/14915 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000098/2024-2025 | 2407/CMD | 02/08/2024 | 31/10/2024 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | SHRIGRAM PIPED WATER SUPPLY SCHEME | SM/14915 | New | Quotation for new service connection at Shrigram PWSS PH-2. |  |  | BILL/00416/2024-2025 | BP-2024-25-222 | 26/07/2024 | 26/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.77 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | SHRIGRAM PIPED WATER SUPPLY SCHEME | SM/14915 | New | Quotation for new service connection at Shrigram PWSS PH-1. |  |  | BILL/00417/2024-2025 | BP-2024-25-221 | 26/07/2024 | 26/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.4 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-I | Central Mechanical | SHRIGRAM PIPED WATER SUPPLY SCHEME | SM/14915 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SHRIGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000832/2023-2024 | 4109/CMD | 29/08/2023 | 28/09/2023 | DUTTA ENTERPRISE | 26.96 | 0 | 0 | 100
Total | [13 empty] | 500.39 | 129.4 | 25.86