## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14917 | New | Material Requisition To Resource Division |  |  | RTOR000349/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 8.77 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14917 | New | Material Requisition To Resource Division |  |  | RTOR000509/2023-2024 | 4033/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 0.33 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14917 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at NAMA BHANDARITURI Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000830/2023-2024 | 4107/CMD | 29/08/2023 | 28/09/2023 | B.P. TRADING CORPORATION | 20.79 | 13.43 | 64.59 | 60
4 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14917 | New | Material Requisition To Resource Division |  |  | RTOR000805/2023-2024 | 304/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 3.84 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14917 | New | New service connection for Nama Bhandartikuri W/S Scheme. |  |  | BILL/02190/2023-2024 | BP-2023-24-385 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.19 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14917 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NAMA BHANDARITURI, SAHAPUR & MOUDANGA Piped Water Supply Scheme under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000511/2023-2024 | 3689/BWD | 23/08/2023 | 01/01/2026 | THE MAHADEV CONSTRUCTION | 734.18 | 75.99 | 10.35 | 50
7 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14917 | New | Different types of works involve in connection with Augmentation of SAJIARA (SM/09716), NAMA BHANDARTIKURI (SM/14917) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000394/2024-2025 | 3010/BWD | 02/08/2024 | 30/03/2025 | PRATIMA CONSTRUCTION | 79.16 | 0 | 0 | 2
8 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14917 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000714/2024-2025 | 2979/CMD | 25/11/2024 | 23/02/2025 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
Total | [13 empty] | 904.54 | 89.41 | 9.89