## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | LAKHURIA PIPE WATER SUPPLY SCHEME | SM/14918 | New | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 1965/BWD | 26/04/2023 | 26/04/2023 | Resource Division | 1.64 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | LAKHURIA PIPE WATER SUPPLY SCHEME | SM/14918 | New | Material Requisition To Resource Division |  |  | RTOR000393/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 5.83 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | LAKHURIA PIPE WATER SUPPLY SCHEME | SM/14918 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000118/2024-2025 | 2590/CMD | 27/08/2024 | 25/11/2024 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | LAKHURIA PIPE WATER SUPPLY SCHEME | SM/14918 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000107/2024-2025 | 485/KTS | 16/04/2024 | 27/06/2024 | AJIT SAMANTA | 0.92 | 0.23 | 25 | 10
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | LAKHURIA PIPE WATER SUPPLY SCHEME | SM/14918 | New | Material Requisition To Resource Division |  |  | RTOR000814/2023-2024 | 295/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 20.47 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | LAKHURIA PIPE WATER SUPPLY SCHEME | SM/14918 | New | Quotation for new service connection at Lakhuria PWSS PH-I. |  |  | BILL/00342/2024-2025 | BP-2024-25-165 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | LAKHURIA PIPE WATER SUPPLY SCHEME | SM/14918 | New | Quotation for new service connection at Lakhuria PWSS PH-2. |  |  | BILL/00345/2024-2025 | BP-2024-25-166 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.69 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | LAKHURIA PIPE WATER SUPPLY SCHEME | SM/14918 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Lakhuria Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000769/2023-2024 | 4067/CMD | 29/08/2023 | 30/05/2025 | GLACIER ENGINEERING CO | 26.98 | 10.58 | 39.22 | 43
9 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | LAKHURIA PIPE WATER SUPPLY SCHEME | SM/14918 | New | Supply and delivery of 10 HP pump motor set at T.W. No - 2 of Lakhuria (Block-Mongolkote) water supply scheme under CMD, PHE Dte. | Driller In-Charge | JUNIOR ENGINEER | ORD/001503/2024-2025 | 128/DIC/BMSD(D) | 20/02/2025 | 27/02/2025 | GLACIER ENGINEERING CO | 0.81 | 0 | 0 | 100
Total | [13 empty] | 129.1 | 10.81 | 8.37