## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14925 | New | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 15.82 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14925 | New | Material Requisition To Resource Division |  |  | RTOR000416/2023-2024 | 3866/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 0.23 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14925 | New | New service connection charges for Bhandarituri PWSS TW-1 |  |  | BILL/01535/2023-2024 | BP-2023-24-202 | 18/10/2023 | 18/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.82 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14925 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at BHANDARITURI Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000816/2023-2024 | 4096/CMD | 29/08/2023 | 28/09/2023 | KAMAKHYA ENTERPRISE | 20.75 | 0 | 0 | 60
5 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14925 | New | BHANDARTIKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000758/2022-2023 | 1280/BWD | 20/03/2023 | 18/06/2023 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. | 65.35 | 0 | 0 | 100
6 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14925 | New | Material Requisition To Resource Division |  |  | RTOR000797/2023-2024 | 312/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 7.05 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Purbasthali-I | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14925 | New | Different types of works involve in connection with Augmentation of DIRGHAPARA (SM/07804) Water Supply Scheme, MOUDANGA (SM/ 14020) Water supply Scheme & BHANDARTIKURI (SM/14925) Water Supply Scheme under Burdwan Division, PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KALNA SUB-DIVISION PHE DTE | ORD/000357/2024-2025 | 2912/BWD | 25/07/2024 | 29/09/2025 | BANSBERIA CONSTRUCTION CO. | 293.38 | 0 | 0 | 22
8 | PURBA BARDHAMAN | Purbasthali-I | Central Mechanical | BHANDARITURI PIPED WATER SUPPLY SCHEME | SM/14925 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000072/2024-2025 | 2397/CMD | 02/08/2024 | 31/10/2024 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
Total | [13 empty] | 457 | 0 | 0