## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | Material Requisition To Resource Division |  |  | RTOR000227/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 8.19 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | Material Requisition To Resource Division |  |  | RTOR000545/2023-2024 | 4299/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 9.65 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | Material Requisition To Resource Division |  |  | RTOR000650/2023-2024 | 5112/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001007/2023-2024 | 2751/BSD | 28/11/2023 | 29/05/2024 | SK.ASFIA | 2.4 | 0.4 | 16.65 | 70
5 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000102/2024-2025 | 2395/CMD | 02/08/2024 | 31/10/2024 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | Restoration Work of damage portion of the RIDF road from Bilbari to Farakpur for PHE pipe laying work within MEMARI-II BLOCK IN THE DISTRICT OF PURBABARDHAMAN |  |  | BILL/00978/2024-2025 | 1052/JJM | 13/11/2024 | 13/11/2024 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 23.03 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | New service connection for Bamunpukur PWSS TW 1. |  |  | BILL/02439/2023-2024 | BP-2023-24-524 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.99 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | New service connection for Bamunpukur PWSS of PH-1 |  |  | BILL/02352/2023-2024 | BP-2023-24-471 | 31/01/2024 | 31/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.81 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | Quotation for new service connection at Bamunpukur PWSS TW-2. |  |  | BILL/00932/2024-2025 | BP-2024-25-349 | 05/10/2024 | 05/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.45 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | BAMUNPUKUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER RWS BURDWAN SUB-DIVISION PHE DTE | ORD/000112/2023-2024 | 2301/BWD | 19/05/2023 | 01/06/2026 | MLG CONSTRUCTION | 447.89 | 161.47 | 36.05 | 62
11 | PURBA BARDHAMAN | Memari-II | Central Mechanical | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bamunpukur Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000710/2023-2024 | 4021/CMD | 29/08/2023 | 01/08/2025 | DUTTA ENTERPRISE | 29.38 | 0 | 0 | 50
12 | PURBA BARDHAMAN | Memari-II | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME | SM/14930 | New | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related(schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-02-2025 to 30-04-2025) |  | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/001402/2024-2025 | 240/BSD | 31/01/2025 | 07/04/2025 | PARVIN BEGAM | 0.85 | 0.28 | 33.33 | 100
Total | [13 empty] | 596.1 | 162.15 | 27.2