## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME | SM/14962 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 32.63 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME | SM/14962 | New | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 4.84 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME | SM/14962 | New | Material Requisition To Resource Division |  |  | RTOR000601/2023-2024 | 4907/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 33.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Bhatar | Central Mechanical | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME | SM/14962 | New | New service connection charges for Bazar Mahammadpur PWSS TW-1 |  |  | BILL/00883/2023-2024 | BP-2023-24-109 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.85 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Bhatar | Central Mechanical | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME | SM/14962 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAZAR MAHAMMADPUR Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000235/2023-2024 | 3171/CMD | 26/07/2023 | 25/08/2023 | SUNRISE ENGINEERING CORPORATION | 27.78 | 0 | 0 | 95
6 | PURBA BARDHAMAN | Bhatar | Central Mechanical | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME | SM/14962 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000067/2024-2025 | 2394/CMD | 02/08/2024 | 31/10/2024 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Bhatar | Central Mechanical | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME | SM/14962 | New | New service connection charges for Bazar Mohammadpur PWSS TW-2 |  |  | BILL/01734/2023-2024 | BP-2023-24-250 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.98 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Bhatar | Burdwan Division | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME | SM/14962 | New | BAZAR MAHAMMADPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000801/2022-2023 | 1529/BWD | 29/03/2023 | 16/01/2025 | ASHOK MITRA | 537.95 | 0 | 0 | 100
9 | PURBA BARDHAMAN | Bhatar | Central Mechanical | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME | SM/14962 | New | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000590/2024-2025 | 3105/CMD | 11/12/2024 | 09/02/2025 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0 | 0
Total | [13 empty] | 746.88 | 0 | 0