## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | Material Requisition To Resource Division |  |  | RTOR000102/2022-2023 | 1637/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 1.93 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 1239/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 5.51 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | New service connection charges of Amilia W/S Scheme TW-2 |  |  | BILL/00679/2023-2024 | BP-2023-24-24 | 21/06/2023 | 21/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.81 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | New service connection charges of Amilia W/S Scheme TW-1 |  |  | BILL/00678/2023-2024 | BP-2023-24-23 | 21/06/2023 | 21/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | AMILIA Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte.,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000737/2022-2023 | 1067/BWD | 13/03/2023 | 07/01/2024 | SHUBHRA KANTI GHOSH | 247.76 | 225.51 | 91.02 | 40
6 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amilia Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000051/2023-2024 | 2515/CMD | 02/06/2023 | 02/07/2023 | MS MANABESH ROY | 28.91 | 23.6 | 81.65 | 90
7 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | Material Requisition To Resource Division |  |  | RTOR000789/2023-2024 | 319/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 21.17 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | Way leave / Track crossing proposal with Application ID: SER-ADRA-2024-WL-114 in IR-RBCS laying of 200 mm dia Carrier pipe with 600 mm dia Casing pipe for water supply on (Jal Jeevan Mission) at KM 317/03 to 317/04 in between Seharabazar (SRBZ) to Kaiyar (KYB) by PHE Dte.,Burdwan Division. |  |  | BILL/01098/2024-2025 | 1184/JJM | 20/12/2024 | 20/12/2024 | INDIAN RAILWAY | 5.32 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period AUG.'2024 to OCT.'2024] |  |  | ORD/000845/2024-2025 | 575/DSD | 19/07/2024 | 05/10/2024 | MD HASIN | 1 | 0.33 | 33.33 | 0
10 | PURBA BARDHAMAN | Khandaghosh | Central Mechanical | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000071/2024-2025 | 2391/CMD | 02/08/2024 | 31/10/2024 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
11 | PURBA BARDHAMAN | Khandaghosh | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME | SM/14963 | New | Survey, planning, design of pipe crossing system by adopting trenchless technologies (e.g. Jack Pushing Method etc.) for crossing Railway, as per relevant I.S. Code with latest amendment, guidelines, specification and requirement of the authorities owning the railway track, submission of design report and drawing obtaining permission on behalf of the PHE Dte. across the railway track between Seharabazar (SRBZ) and Kaiyar (KYB) Station & connecting with existing 160mm dia HDPE distribution main line of AMILIA Water Supply Scheme of Khandaghosh Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/001308/2024-2025 | 938/BWD | 11/03/2025 | 10/04/2025 | MANASH GHOSH | 30.33 | 0 | 0 | 0
Total | [13 empty] | 394.43 | 249.44 | 63.24