## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14965 | New | Material Requisition To Resource Division |  |  | RTOR000226/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 4.92 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14965 | New | Material Requisition To Resource Division |  |  | RTOR000496/2023-2024 | 4020/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 0.41 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14965 | New | Material Requisition To Resource Division |  |  | RTOR000651/2023-2024 | 5113/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.46 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14965 | New | New Service connection for Bamchandrapur PWSS TW-2. |  |  | BILL/02893/2023-2024 | BP-2023-24-626 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.71 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14965 | New | New Service connection for Bamchandrapur PWSS TW-1. |  |  | BILL/02894/2023-2024 | BP-2023-24-627 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.75 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan-II | Burdwan Division | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14965 | New | BAMCHANDRAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | Junior Engineer, Burdwan Sadar Sub-Division | ORD/000196/2023-2024 | 2701/BWD | 08/06/2023 | 02/10/2025 | M/S PROCHESTA ENTERPRISE | 254.91 | 70.2 | 27.54 | 60
7 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14965 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bamchandrapur Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER | Junior Engineer | ORD/000734/2023-2024 | 4044/CMD | 29/08/2023 | 28/09/2023 | S.K. ENTERPRISE | 30.08 | 0 | 0 | 90
8 | PURBA BARDHAMAN | Burdwan-II | Central Mechanical | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME | SM/14965 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | ASSISTANT ENGINEER | Junior Engineer | ORD/000065/2024-2025 | 2389/CMD | 02/08/2024 | 31/10/2024 | DILIP MAHATO | 53.14 | 0 | 0 | 12
Total | [13 empty] | 375.38 | 70.2 | 18.7