## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME | SM/14966 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHARKHI & SHIBNUL Piped Water Supply Scheme under KETUGRAM-II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000049/2023-2024 | 1823/BWD | 18/04/2023 | 01/11/2026 | PASCON | 723.75 | 206.17 | 28.49 | 35
2 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | CHARKHI PIPED WATER SUPPLY SCHEME | SM/14966 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHARKHI Water Supply Scheme [ Block- KETUGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000391/2023-2024 | 3663/CMD | 01/08/2023 | 01/06/2025 | AHALYA ENGINEERING WORKS | 27.78 | 21.5 | 77.41 | 48
3 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME | SM/14966 | New | Material Requisition To Resource Division |  |  | RTOR000488/2023-2024 | 4012/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 0.69 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME | SM/14966 | New | Material Requisition To Resource Division |  |  | RTOR000622/2023-2024 | 4880/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 29.6 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | CHARKHI PIPED WATER SUPPLY SCHEME | SM/14966 | New | New service connection charges for Charkhi PWSS TW-2 |  |  | BILL/00880/2023-2024 | BP-2023-24-110 | 09/08/2023 | 09/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.25 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | CHARKHI PIPED WATER SUPPLY SCHEME | SM/14966 | New | Quotation for new electric service connection at Charki PWSS TW No-1 |  |  | BILL/01744/2023-2024 | BP-2023-24-251 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | CHARKHI PIPED WATER SUPPLY SCHEME | SM/14966 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 31/10/2024 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME | SM/14966 | New | Balance work for OHR, extension of pipeline to provide FHTC with land development, plinth protection for pump house & OHR under Charkhi PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000312/2024-2025 | 2836/BWD | 19/07/2024 | 01/11/2026 | PASCON | 74.08 | 0 | 0 | 90
9 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME | SM/14966 | New | Material Requisition To Resource Division |  |  | RTOR000770/2023-2024 | 194/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 9.75 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME | SM/14966 | New | Balance work such as Road restoration and other ancillary work for Charkhi PWSS (SM/14966) under KETUGRAM-II Block under Katwa Sub-Division under Burdwan Division, PHED, District:- Purba-Bardhaman (Sl No-6) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000938/2025-2026 | 1655/KTS | 02/07/2025 | 01/08/2025 | PASCON | 4.82 | 0 | 0 | 0
Total | [13 empty] | 921.92 | 227.67 | 24.7