## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | Material Requisition To Resource Division |  |  | RTOR000115/2023-2024 | 1965/BWD | 26/04/2023 | 26/04/2023 | Resource Division | 2.48 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | Material Requisition To Resource Division |  |  | RTOR000336/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 1.47 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Mangolkote | Central Drilling | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilising Departmental Machineries for MAHARUTBA W/S Scheme (T/W-I), Mongalkote Block under Purba Bardhaman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000157/2023-2024 | 1819/CDD | 07/12/2023 | 06/01/2024 | M/S PRACHI ENGINEERING | 13.67 | 13.12 | 95.99 | 100
4 | PURBA BARDHAMAN | Mangolkote | Central Drilling | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for MAHARUTBA W/S Scheme (T/W-II) Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 1338/CDD | 13/09/2023 | 13/10/2023 | C.M. ENTERPRISE | 11.46 | 4.59 | 40.1 | 100
5 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | Material Requisition To Resource Division |  |  | RTOR000815/2023-2024 | 296/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 20.47 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | NEW SERVICE CONNECTION FOR MAHARTUBA PWSS. |  |  | BILL/02860/2023-2024 | BP-2023-24-610 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.94 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | Quotation for new service connection at Mahartuba PWSS PH-1 |  |  | BILL/00385/2024-2025 | BP-2024-25-206 | 18/07/2024 | 18/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHATPARA & MAHARUTBA Piped Water Supply Scheme under Mangolkote Block, District:-Purba-Bardhaman [NEW SCHEME] | Assistant Engineer | J.E. katwa,Junior Engineer | ORD/000429/2023-2024 | 3328/BWD | 02/08/2023 | 01/10/2025 | KAMIRUL SK & CO. | 815.64 | 266.02 | 32.61 | 10
9 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Maharutba Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | ASSISTANT ENGINEER,Driller In-Charge | Junior Engineer | ORD/000775/2023-2024 | 4069/CMD | 29/08/2023 | 28/09/2023 | GLACIER ENGINEERING CO | 26.98 | 0 | 0 | 44
10 | PURBA BARDHAMAN | Mangolkote | Central Mechanical | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | Junior Engineer | ORD/000097/2024-2025 | 2406/CMD | 02/08/2024 | 19/05/2025 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
11 | PURBA BARDHAMAN | Mangolkote | Burdwan Division | MAHARUTBA PIPED WATER SUPPLY SCHEME | SM/14970 | New | Balance work of MAHARTUTBA Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman | Assistant Engineer | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/001212/2024-2025 | 722/BWD | 24/02/2025 | 24/06/2025 | KAMIRUL SK & CO. | 147.19 | 0 | 0 | 0
Total | [13 empty] | 1109.94 | 283.74 | 25.56