## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHARKHI & SHIBNUL Piped Water Supply Scheme under KETUGRAM-II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE,JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000049/2023-2024 | 1823/BWD | 18/04/2023 | 01/11/2026 | PASCON | 723.75 | 174.88 | 24.16 | 35
2 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Shiblun Water Supply Scheme [ Block- Ketugram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000490/2023-2024 | 3798/CMD | 10/08/2023 | 09/09/2023 | S.P. CONSTRUCTION | 26.96 | 16.04 | 59.51 | 48
3 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 1.1 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 75.98 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | Material Requisition To Resource Division |  |  | RTOR000759/2023-2024 | 5246/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 18.9 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | Material Requisition To Resource Division |  |  | RTOR000487/2023-2024 | 4011/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.1 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | New service connection charges for Shiblun PWSS TW-2 |  |  | BILL/01355/2023-2024 | BP-2023-24-133 | 22/08/2023 | 22/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.04 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000103/2024-2025 | 2408/CMD | 02/08/2024 | 31/10/2024 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | Balance work for OHR, extension of pipeline to provide FHTC with land development, plinth protection for pump house & OHR under SIBLUN PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan Division PHE Dte. | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000311/2024-2025 | 2835/BWD | 19/07/2024 | 01/11/2026 | PASCON | 84.02 | 0 | 0 | 80
10 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | REVISED QUOTATION FOR NEW SERVICE CONNECTION AT SHIBLUN PWSS TW-1 |  |  | BILL/00369/2024-2025 | BP-2024-25-190 | 08/07/2024 | 08/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.19 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Ketugram-II | Central Mechanical | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | New service connection charges for Shiblun PWSS TW-1 |  |  | BILL/01898/2023-2024 | BP-2023-24-368 | 15/01/2024 | 15/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.19 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ketugram-II | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME | SM/14972 | New | Balance work such as Road restoration and other ancillary work for Shiblun PWSS(SM/14972) under KETUGRAM-II Block under Katwa Sub-Division under Burdwan Division, PHED, District:- Purba-Bardhaman (Sl No-5) | Assistant Engineer | JUNIOR ENGINEER KATWA SUB-DIVISION PHE DTE | ORD/000937/2025-2026 | 1654/KTS | 02/07/2025 | 01/08/2025 | PASCON | 4.8 | 0 | 0 | 0
Total | [13 empty] | 996.97 | 190.92 | 19.15